## Sheet1
Item No. | Meeting Date | Responsibility | Due date | Status | Commentary
Handover Zoom Telecon 13-May-2020
| Present |  |  |  | AI, AW, BB, DD, IR, JL, MF, MM, MS (outgoing chair)
20.1.1 | Contact all members in near future to gauge continued interest in MNF | AI, IR | ?? | Closed | AGM notes captured response to optional question.
20.1.2 | Identified and publish key general themes with the AGM minutes, noting that there is strong support to resubmit for Designation | AW | ?? | Closed
20.1.3 | Place suitable message from new co-chairs on website along with the AGM results | AI, IR | ?? | Closed
20.1.4 | Change Authorised Signatories in the current NatWest Bank mandate, for the accounts detailed in section 1.3 (of what?) | BB | ?? | Closed
20.1.5 | Pass currently held banking documents to to BB | AW | ?? | Closed
20.1.6 | Agree transfer and amend responsibility for website, mailchimp and Facebook | MS, AI, IR | ?? | Closed | Some issues regarding stability of MNF Roundcube email raised. New issue.
20.1.7 | Hand main email account chair@mnf.org.uk password to both co-chairs | MS, AI, IR | ?? | Closed
20.1.8 | Change forwarding rules to remove MS and send incoming emails onwards to AI and IR personal accounts | AI, IR | ?? | Closed
20.1.9 | Transfer previous Cox Green and Maidenhead Neighbourhood Forum files and papers to AI and IR | MS, AI, IR | ?? | Closed | Digital record to AI, Documentary records to IR
20.1.10 | Set up a WhatsApp group for the Management Committee | BB | ?? | Closed | Agreed not to use as not all members of the MC have a Smart Phone
20.1.11 | Decide when next to have a Management Committee meeting | AI, IR | ?? | Closed | Dates provisionally agreed
20.1.12 | Decide setup of Forum meetings and Management meetings, until Covid-19 restrictions end, and after | AI, IR | ?? | Closed | Arrangements for reopening up of MNF from Hibernation to be finally agreed once clarification on easing of COVID-19 restrictions is given. Noted however that with the recent Planning Applications for the Town Centre there is a need to consider the MNF position.
Item No. | Management team Zoom Telecon 17-Jun-2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, AW, BB, DD, IR, JL, MF, MM
20.2.1 | Follow up from zoom meeting with Cllr David Coppinger to arrange meeting with new Head of Planning | AI, IR | 2020-06-19 | Closed | Email sent after this MC zoom meeting. Awaiting response.
20.2.2 | Agree schedule and structure of management meetings and full Forum meetings | Mgt Ctte. | By when? | Closed | Proposed that MC meetings are planned for 2 weeks before full Forum meetings. (Planned for 1st Wednesday of the month).
20.2.3 | Communications to/from other groups/people/website | Mgt Ctte | 2020-07-22 | Closed | Item deferred to next meeting
20.2.4 | Need for response/action as a group to the various Planning applications affecting the Town Centre - Nicholsons | Mgt Ctte | 2020-06-26 | Closed | AI to draft text of note to seek views of the Members on Nicholson/Areli planning application 20/01251 together with a short questionnaire Noting that although the MNF is not formally recognised by RBWM, there is a need to represent the views of the membership/wider community as a body.
20.2.5 | Publish views on Nicholson/Areli application after obtaining membership views. | AI, IR+? | 2020-07-03 | Closed | Consider wider circulation on Nicholson/Areli application 20/01251 via Facebook/letter to the Advertiser. Decide whether MNF wants to make a formal representation to the Planning Application: consultation expires 14-Jul-20.
20.2.6 | As a minimum MNF needs to signpost significant planning applications, and other planning proposals affecting the town and which may impact on a future Neighbourhood Plan. | Mgt Ctte | 2020-07-22 | Closed | See 3.6 below
20.2.7 | Response to BLP given that the Inspector has resumed the process | IR/AW | 26/06/2020 | Closed | AW/IR to review recent comments from the Planning Inspector in relation to the MNF original submission and report back. Comments submitted 07 August 2020.
20.2.8 | Initial outline scope of MNF future work and resourcing, roles and skills |  | 2020-07-22 | Pending | Out of time - not discussed Item has been considered in the context of wider discussions with RBWM. Update 18/11/2020: Until a way forward on the Plan Area is found this item is pending
20.2.9 | Agenda items for future management meeting |  | 2020-07-22 | Closed | Out of time - not discussed
20.2.10 | Budget and grant application | AW/BB | 2020-06-26 | Closed | AW to discuss with Locality process for grant application. BB to discuss with AI/IR the development of the budget for the proposed activities for the rest of this year.
20.2.11 | Zoom professional subscription | AI | 2020-06-26 | Closed | Professional subscription to be obtained to facilitate on-line meetings (£11.99/month)
Item No. | Management team Zoom Telecon 01-Jul-2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, AW, BB, DD (part), IR, JL, MF, MM
20.3.1 | Response to Areli Planning Application for Nicholsons | AI/IR | 2020-07-06 | Closed | Prepare a draft response from MNF based on Viewpoint articles on the web and any other comments from members.
20.3.2 | Meeting of full Forum | AI | 2020-07-06 | Closed | Investigate zoom meeting for all members using a presentation format to discuss current topics affecting the Forum. Suggested date Wednesday 08 July at 1900. In the event this did not take place as there was insufficient time to prepare material for a worthwhile discussion.
20.3.3 | Budget and grant application | BB/AW/AI | 2020-07-15 | Closed | AW has obtained grant application form which needs to be submitted electronically to Locality by 15 July. AW to recirculate last years budget to use as a base for this years proposal
20.3.4 | AECOM Technical Support package | AW | 2020-07-10 | Closed | AW to confirm status of existing TS package which may be still available
20.3.5 | Significant Planning Applications | AI | 2020-07-10 | Closed | Agreed that significant large applications and other major projects affecting Maidenhead should be signposted on the web site where details are known.
20.3.6 | Formal Areli proposal comment to RBWM Planning | AI/IR | 2020-07-14 | Closed | Agreed MNF formally comments on the application, using view points published on web plus any comments received from members, and submit to RBWM Planning by 14 July.
20.3.7 | Statesman House | AI/IR/MF | 2020-07-14 | Closed | Agreed that MNF review and comment due to impact on wider schemes in Maidenhead e.g. Golf Course/Missing Links project and JTP Vision and Charter ideas> Note: No MNF submission made on Statesman House.
Item No. | Management team Zoom Telecon 22-Jul-2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL, DD, MM, AW
20.4.1 | Matters arising from 3.7 above | AI/IR | 2020-08-19 | Closed | Agreed that only sites identified in BLP should be considered, or over 50 dwellings on a 'windfall' site (i.e. a site not identified in the BLP)
20.4.2 | Publication of article prepared by Richard Davenport on CIL | AI | 27/072020 | Closed | Agreed that circulated article should not be published by MNF. Topic under discussion in RBWM Overview and Scrutiny Panel. Note: Copy of Richard Davenport's note passed to Cllr John Baldwin (Lib Dem) for information.
20.4.3 | Funding | AW | 2020-08-19 | Closed | AW submitted grant application for £2313.93 on 14 July 2020, awaiting response from Locality. Post meeting note: Contact made by Locality regarding application, grant application is being reviewed, initial support is likely to be via an enhance technical support package with AECOM and other consultancies to support community engagement, before awarding a grant package. Locality has forwarded application to MHCLG for authority to proceed with support package. Further details within 2 weeks. See item 5.5 below for update.
20.4.4 | BLPSV - Response to inspector's MIQs | IR/AW | 2020-07-31 | Closed | Draft response to BLP inspectors MIQ to be circulated before submission
20.4.5 | Designation | AI | 2022-08-19 | Closed | Contact Adrien Waite regarding meeting regarding designation
20.4.6 | Designation | AW | 2022-08-19 | Closed | Review status of NF/NPs in previous LPAs where Head of Planning previously worked. Hertsmere BC: 1 NF Designated (Shenley) - a rural parish council with c.4300 population. 1 NP pre submission consultation (Radlett) Aldenham Parish Council with c. 10,000 population Watford BC: Nil LB Hillingdon: 1 NF Designated (Ickenham) c.12000 population
20.4.7 | Future meetings | AW | 2022-08-19 | Closed | Note URC is still not hosting meetings due to the ongoing situation. Zoom meeting for all members is still a possibility, felt it probably should wait until after meeting with Adrien Waite and the position is clearer. Working assumption is that 'normal' activity could start to resume after 01 September 2020. Post meeting note - latest guidance suggests October at the earliest, with a preference for non-essential meetings to continue to be held on-line. Update 19/08/2020 - URC is still closed. Secretary to make contact with Church for an update. Update 18/11/2020 - With the reintroduced Lockdown, URC is once again closed. Previous discussion suggested that we would need to undertake our own risk assessment to be able to use facility when gatherings are permitted again. Note: our hire was originally until end of December 2020, we have used the facility on 2 occasions and cancelled on 1 occasion before Covid-19 affected the ability to meet. Currently from Jan 2021 we have no meeting room booked and no funds to pay for one!
20.4.8 | AOB | AI/IR | 2020-08-19 | Closed | It was felt that we should gather information (where known) about issues affecting the NP area and include on the website
Item No. | Management team Zoom Telecon 18-Aug-2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL, DD, MM, MF, AW
20.5.1 | Communications to/from other groups/people/website | AW | 2020-08-19 | Closed | Contact made by Wimbledon NF wanting to share our experiences of developing a Neighbourhood Plan and seeking Designation with them. This followed a recommendation by AECOM. AW provided background information as to the work of MNF so far.
20.5.2 | Communications to/from other groups/people/website | JL/MM | 2020-08-19 | Closed | Request to ensure that our communications reach the disability groups in Maidenhead. Note: MM is compiling a list of faith groups based on list previously used. Suggestion that the library keeps details of community groups which could be included in a mailing Please send any contact details to MM of groups which may be interested in being involved.
20.5.3 | Letter to faith groups | MM | 2020-09-02 | Closed | MM has circulated a draft letter for comment to be sent out to the faith groups seeking new members for MNF. MM will recirculate the letter, any comments to Martin. Agreed letter should be posted out rather than hand delivered. Letter was prepared and circulated but due to uncertainty of the activities of the Forum not distributed. See 5.14 below
20.5.4 | Addition of development map to the MNF website | AI | 2020-09-23 | Closed | Discussion on the draft development map circulated by AI, idea welcomed. Request to include more details if possible, perhaps with some kind of layered map similar to the RBWM Neighbourhood Map. Update 18/11/2020: AI to develop a suitable map Update 20/01/2021: Simple map and description added to website Jan 2021
20.5.5 | Funding | AW | 2020-09-23 | Closed | AW has been in dialogue with Locality (Dave Chapman) concerning further financial support following our grant application. Technical Support has been awarded to assist the Forum with designation but further refinement of scope is necessary before the grant application will be considered. This will be established during the review of our designation by Locality. An initial discussion (by zoom) with a technical advisor (David Moynihan) has taken place on 18/08/2020, a summary of our progress to date has been provided together with various supporting documents. Once these have been reviewed by DM a further meeting with the co-chairs /MC will need to be arranged to discuss next steps. Further support has been provided by Locality through Dave Chetwyn from consultancy UVE, who will assist with public engagement. Update 18/11/2020: AW had a discussion with Dave Chetwyn to seek guidance on a way through this issue with RBWM. Key points being we need to focus on increasing representation from all sections of the community and possibly consider a reduced area (possibly excluding established residential areas and green belt). DC offered to discuss with RBWM the issue of refusal for the Area and Forum - legally the 2 are separate. Update 20/01/2021: AW has secured a small interim grant from Locality see below for details.
20.5.6 | Designation | AI/IR | 2020-09-23 | Closed | Adrien Waite has been offered dates of 7-Sep and 9-Sep for a meeting in email sent on 17th August, no response so far. Note: Virtual meeting held 12 October 2020
20.5.7 | Planning for the Future - White Paper | All | 2020-09-23 | Closed | Following a brief discussion felt that MNF should submit a response to the Planning White Paper. All members to read up on the document before the zoom meeting to discuss a suitable response.
20.5.8 | Planning for the Future - White Paper | AI/IR | 2020-09-22 | Closed | To organise a 1 hour zoom discussion before next MC meeting. Note: Held on 14 October 2020
20.5.9 | Planning for the Future - White Paper | AI | 2020-09-23 | Closed | A suitable item to be included on the website, focussing on main aspects of the proposed changes
20.5.1 | Local Heritage Listing | AI | 2020-08-19 | Closed | Noted that following discussion with the Maidenhead Civic Society, this joint project to record local historic buildings which are not Listed, has been put on hold until such time as conditions allow a kick off event to be held.
20.5.11 | Local Heritage Listing | MM | 2020-08-19 | Closed | Noted that in a recent Planning Application rejection for redevelopment of New Kingswood, Lower Boyndon Road (20/00950, the RBWM Planning team quoted the importance of non-listed heritage features in the area as a reason for refusing Planning Permission.
20.5.12 | RBWM Climate Emergency and Environment Strategy | AI/AW | 2020-09-23 | Closed | MNF has been invited to consultation workshops on this strategy, (we were participants in the original workshops). The Strategy is about the internal RBWM policy not the borough area itself. AI/AW to review whether we need to be involved further. Note: This is different to the RBWM Climate Emergency Coalition - co-founded by Sarah Bowden, (who is one of our members). It was acknowledged that our support for the wider CEC objectives should be followed in the MNF draft NP policies. Submission made, using Mark Fessey's input (thanks Mark).
20.5.13 | MNF Facebook Page | AI | 2020-08-19 | Closed | Note that MNF does have a FB page and that there is interest in the activities of MNF via this page.
20.5.14 | Diversity and Inclusion | MM | 2020-09-23 | Pending | Agreed that MM would keep a listing of the various faith and cultural groups as potential supporters of MNF Update 18/11/2020: Agreed to expand list to include all community organisations. List to be shared with MC members.
Item No. | Management Committee zoom meeting 23 Sep 2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL, DD, MM, MF, AW
20.6.1 | Planning for the Future - White Paper Consultation response | IA/IR | 2020-10-14 | Closed | Summary of the consultation proposals prepared by IR circulated, with a view to the Management Committee selecting which areas to comment on. Agreed to circulate a summary list of all MHCLG proposals to the Forum membership for comments to include in an MNF response. IR to include Proposal 12, currently missing. Note: Survey held - 35 responses
20.6.2 | Designation | IA/IR | 2020-10-14 | Closed | Note no response yet from RBWM. Agreed to write formally to Adrien Waite requesting meeting, if lack of co-operation continues need to escalate to leader of the council and Theresa May as our MP. Post meeting note: Letter sent 24 September 2020.
20.6.3 | Designation | IA/IR | 2020-10-14 | Closed | Concern expressed by AI that the ongoing lack of progress with MNF and a recent review of the BLPSV-PC by IR suggests that the policy space left for a made NP has diminished. Almost to the point of is it worth the effort. After a discussion it was noted that the existing RBWM policy and NPPF both recognise the need for local community involvement via the NP process. MF commented that Slough BC has recently published a policy on growth (densification) in the suburbs, there is the possibility RBWM may over time have to follow suit. This suggests that a NP focussed on the non-town centre areas may still have relevance. Until the Inspector has opined on the BLPSV-PC we won't know what the future policy space looks like. Many of the general policies which may be listed as strategic, may still have scope for local detailed policies to be developed.
20.6.4 | Funding | IA/AR/AW | 2020-10-14 | Closed | A initial discussion has been held with Locality to ascertain what support then can offer to help the Forum on its journey to becoming designated. They have offered to assist with contacting RBWM, and potentially assisting with identifying potential policy space. Update 18/11/2020: Once we have some clarity with RBWM as to what is acceptable for the NP area, we will be able to resume funding discussions with Locality. Update 20/01/2021: Interim funding agreed see below
20.6.5 | RBWM Climate Emergency and Environment Strategy | MF | 2020-09-28 | Closed | Agreed MF to produce brief summary to form our response to this proposed policy, closing date 18:00 29-Sep-20. If OK, MNF will send as a group response. Note: the draft was reviewed by co-chairs, MF sent on behalf of MNF.
20.6.6 | RBWM A308 consultation | AW/DD | 2020-10-09 | Closed | DD informed the meeting that RBWM is holding a consultation on the A308 corridor through the borough. Some concern that given the amount of development which will eventually be connected into the A308, RBWM may be seeking to upgrade the route. Agreed to circulate link to all members for them to comment. AW to prepare a submission on behalf of MNF Note: No comments received and no submission made on behalf of MNF
20.6.7 | BLP Inspection - Impact of revised housing numbers | AW | 2020-09-25 | Closed | AW has received correspondence from BLP Inspector seeking comments on RBWM response to revised housing numbers, which envisges no change to current requirement as stated in BLP. Seems RBWM is using complex legal analysis to justify its position. Agreed to circulate to MC members for comment.
20.6.8 | Proposed future Topic Papers | JL |  | Pending | JL has offered to prepare topic papers on Childrens facilities - e.g. lack of outdoor paddling pools and play facilities and on Affordable Housing. These can then be published via the website. Update 18/11/2020: JL waiting to see outcome of area discussions before creating further topic papers.
Item No. | Management Committee zoom meeting 14 Oct 2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL, DD, MM, MF, AW
20.7.1 | Feedback from meeting with RBWM (notes circulated earlier) | All | 2020-11-18 | Closed | RBWM concerned about the size of the proposed plan area and the ability of a small group of 21 individuals to deliver a NP. Need to explore whether a 'Federated MNF' with separate area sub-groups within MNF, working under an 'umbrella' organisation could be made to work and be acceptable to RBWM. This could possibly exclude certain small areas of Maidenhead. Suggestions welcome to Andrew/Ian as to possible sub-divisons within the overall MNF area. E.g. groups of Wards, North/South of the A4, East/West of the A308. Possible options can then be discussed with the Head of Planning to establish if there there is a prospect of the MNF being designated. RBWM are willing to work with us to find a way forward and welcomed the constructive dialogue in the meeting. Update 20/01/2021: Due to Head of Planning being off work due to sickness no meeting has been arranged - see below.
20.7.2 | MHCLG - Consultation on Planning White Paper | All | 2020-10-21 | Closed | Meeting discussed potential response to the MHCLG consultation, based on response to MNF members survey. The survey response indicated several consultation areas which most favoured. The Ctte felt that there were possible other questions which should be responded to. IR to draft a response taking preferences and comments from Forum members onboard, in order to prioritorise those proposals we should respond to. If anyone is willing to draft a response on these, or any other of the proposals, please forward your draft to Ian for inclusion by the end of Sun 18-Oct. Agreed to hold an hour zoom call on Wednesday 21 October to run through the draft response before submitting to MHCLG before the closing date of 29 October 2020.
20.7.3 |  | AW | 2020-10-21 | Closed | AW to circulate Planning White Paper Briefing Note produced by Locality (Dave Chetwyn)
Item No. | Management Committee zoom meeting 21 Oct 2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL, DD, MF, AW - Apologies: MM
20.8.1 | MHCLG - Consultation on Planning White Paper | IR | 2020-10-29 | Closed | Each proposal and associated questions were discussed, prioritorising those which had received most comments by the members. Time allowed for additional proposals to be responded to. Response listed below:
Proposal 1 - No - concerns expressed over the funding for the proposal
Proposal 7 - Yes - New technology should be free at the point of use
Proposal 12 - Yes - concerns about funding of process, and the question of creating local/regional architectural character
Proposal 14 - No. Beauty is subjective and there are more important factors to be considered e.g. size of living spaces.
Proposal 17 - Yes
Proposal 18 - Yes but should be aiming for an earlier date
Proposal 19
Question 22(a) - Yes - given Maidenhead as an example
Question 22(b) - Locally but with a caveat e.g. a minimum level
Question 22 (c ) - No Affordable House should not come from CIL
Question 22(d) - No view (LA finance arrangements)
Proposal 9 - Yes
Question 13(a) - Yes
Question 13(b) - Yes - design tools should be free at the point of use
IR to finalise draft response based on discussion and circulate for one last comment before submission. Submmission made on 28 October 2020
Item No. | Management Committee zoom meeting 18 Nov 2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL, DD, AW, MM
20.9.1 | Open items from previous meetings updated | AW | 2020-11-18 | Closed
20.9.2 | Designation - Alternative NF/NP structure | AI/IR | 2020-12-16 | Closed | Given refusal to designate the original NP area, we briefly explored the option for a Forum with 'sub-areas' incorporated in the Constitution of the NF. IR has proposed a 2 sub-area Forum, MF a 4 sub-area Forum. Unfortunately Mark could not be present for the meeting, so we briefly discussed various options ideas. The key point being that Windsor NF was designated with an area of around 32,000 population. We need to discuss whether a similar area for MNF would be acceptable and if so would a 'federated' NP Area work with designated area sub-groups in the Forum Constitution. Agreed: AI to draft a paper for discussion with RBWM and to circulate for comment before neeting RBWM. AI also to try and arrange a discussion with Adrien Waite before our next meeting (16/12/2020). Update 20/01/2021: Paper revised and updated awiting discussion with RBWM
Item No. | Management Committee zoom meeting 16 Dec 2020 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL (part), DD, AW, MM, MF
20.10.1 | Progress with RBWM | AI/IR | 2021-01-20 | Closed | The proposed meeting with Adrien Waite has had to be further postponed due to AW being off sick. We have proposed tentative dates for January 2021. Update 20/01/2021: No dates currently arranged due to lack of commumication from RBWM
20.10.2 | Changes to the proposed MHCLG formula for allocating house building targets for each Local Authority. | All | 2020-12-16 | Closed | Note recent announcement following pressure from certain MPs on the original proposed algorithim. This is likely to reduce some pressure in the South East, with some 20 LAs being specifically identified as areas of growth. Post Meeting Note: Mark has circulated a list of affected LAs.
20.10.3 | BLP Progress | IR | 2020-12-16 | Closed | MM has provided a summary provided by a Civic Society member summarising the current status of the BLP following the recent public examination by the Inspector (IR to circulate after the meeting).
20.10.4 | Revised MNF organisation structure | AI/IR/AW | 2021-01-20 | Closed | Discussion on the notion of a 'federated' Forum with 2-sub areas North and South of the A4, as outlined in Andrew's paper. This paper is intended to be used to sound out RBWM's view on presenting a Forum which was capable of being designated. By formally constituting sub-groups, this is seen as a way of addressing some of the issues raised in the previous refusal to designate letter, together with an increase in supporters and followers as per Andrew's paper. It was felt that the wording of the discussion paper needed to be amended to make the structure of the proposed organisation clearer. AW agreed to prepare a draft of a the MNF Constitution suitable amended to shown what the proposed changes would look like.
20.10.5 | Survey relating to the proposal to use the Golf Course site for housing | AI | 2020-12-31 | Pending | A draft set of potential survey questions has been created with a view to send out to members early in the New Year.
20.10.6 | Producing an informative map to show the current developments in town. | AI/MF/MM | 2020-12-31 | Closed | Andrew shared his initial ideas for a map to go on the Web-site to show outline details of the development sites in the town. The idea was welcomed, however in the ensuing discussion it became apparent that there is too much information to cram on a simple map, it requires mapping Software to enable a layered map to be produced. Martin has agreed to fact check each of the development site texts. Post meeting note - Mark has offered to assist with the mapping aspects.
20.10.7 | End of year message | AI/IR | 2020-12-31 | Closed | Agreed a brief update should be sent round to members as to current activities and status of the Forum.
Item No. | Management Committee zoom meeting 20 Jan 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL DD, AW, Apologies MM, MF (due to change of meeting time at short notice)
21.1.1 | Funding | BB/AW | 2021-01-31 | Closed | AW advised that an interim grant of £400 has been awarded by Locality due to be paid in the next 5 days (via Maidenhead Civic Society) Post meeting note: The £400 grant has now been received into the MNF bank account
21.1.2 | Development sites | AI/AW | 2021-03-31 | Closed | The development sites map/text now posted on the website and boosted on Facebook - this has raised lots of interest and a few questions which Andrew is dealing with. Action: Agreed to quarterly updates with next review towards the end of March. This could include the Missing Links note prepared by AW and the Highways improvement schemes now underway (AW to prepare note).
21.1.3 | Planning applications (Proposal to build flats on land at the rear of the old post office) | AI/IR | 2021-01-31 | Closed | Arising from a recent Planning Application by the Shanly Group to build c.100 flats on West Street (which abuts the rear of properties on the High Street), a discussion took place as to whether MNF should be responding to this and other applications in the town, as this activity overlaps with the work that the Planning Group within MCS does in monitoring and responding to planning applications. The outcome of the discussion was that for this development MNF would not respond, any comments MC member may have can be fed directly to MM to support his response for MCS. It was felt that the larger applications should still be reviewed by MNF (Management Committee) and a link provided on the website to alert members to the planning application.
21.1.4 | BLP update | MM | 2021-02-17 | Closed | MM was unable to join the meeting to provide an update on the BLP inspection. It is understood that the Inspector is preparing her report which may recommend some changes and possible further consultation. Update at next meeting.
21.1.5 | Designation update | AI | 2021-02-17 | Closed | It is understood that Head of Planning (HoP) is now back at work but so far has not responded to our requests for a meeting. Action: AI to make contact with Cllr. Coppinger to find a way to unblock this seeming impasse. Post meeting note: Since the meeting, Andrew has spoken with Cllr Coppinger who advises that for personal family reasons Andrien Waite remains off work.
21.1.5 | RBWM Housing Strategy Paper | AI | 2021-01-31 | Closed | The stategy paper has been reviewed by members and generally felt that it lacks substance. Agreed: MNF not to respond - to be signposted on website.
21.1.6 | RBWM Walking and Cycling Covid consultation | DD/AI | 2021-01-31 | Closed | Some members have read the proposals in the consultation paper. Agreed not to submit a formal response. Action: DD to provide short explanatory paragraph for posting on Website with a link to the consultation.
21.1.7 | Development growth and CIL/S106 contributions | AI | 2021-01-20 | Pending | Andrew/Richard Davenport have undertaken a review of the CIL/S106 contributions received by the Borough. This shows quite clearly that the level of contribution is falling relative to the projected growth in the town. We recognise that this is a politically delicate subject particularly with the current RBWM constrained. The information is important but requires an appropriate opportunity to share it. Agreed to hold for use at a future date
Item No. | Management Committee zoom meeting 17 Feb 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL, DD, AW, MM, MF, RD
21.2.1 | New member of the Management Committee | IR | 2021-02-17 | Closed | Richard Davenport (RD) has been co-opted onto the Management Committee, Richard was welcomed by Ian to the Committee and Ian will brief Richard on the ongoing work of MNF including the options for designation.
21.2.2 | Progress with discussions with RBWM | AI/IR | 2021-02-28 | Closed | Andrew reported on the lack of progress in RBWM engaging with MNF, this is seriously impeding our ability to move forward as a group. Note that the new Head of Place (Andrew Durrant) has recently been appointed, Adrien Waite will ultimately report to this position. Due to the uncertain timescale as to when AD will be in post, agreed to try once again via David Coppinger as lead member, before escalating up to the Leader of the Council. Several members noted that through their relations with RBWM on other projects, communication is proving to be difficult. Post Meeting note: Andrew has emailed DC to try and unblock the situation - response awaited
21.2.3 | MHCLG Design Code Consultation | IR/All | 2021-03-17 | Closed | MHCLG has issued a brief consultation which is seeking input from interested parties on both amendments to the NPPF and the proposed new Design Code. Deadline for responses is 27 March 2021. Agree that Ian will set a schedule for internal responses, then draft a collated MNF response for review at the next meeting.
21.2.4 | Think Piece on Flats v. Houses in Maidenhead | IR/AI/MM | 2021-04-30 | Defer | Based on information provided by MNF, property Journalist, Liam McCarten, has produced a draft article on the Flats v. Housing situation in Maidenhead. This considers the impact of the emerging market conditions and the impact the likely changes with have as a result of the pandemic i.e. more working from home/less travelling to work. The most recent LA Monitoring Report illustrates the disparity between the number of flats available in the town compared to the number of houses; recent planning applications are continuing this trend resulting in a significant imbalance. Concern was expressed that 'Affordable Housing' is often confined to flatted provision rather than family homes, and that the initial site allocations for the Golf Course site suggest that the 600 'Affordable Homes' will be largely flats. It was felt that whilst this is a very significant issue, MNF needs to be cautious with the position it takes. Noted that a new LA Monitoring report is due out in March and that the LMcC article should wait until it can be updated and then consideration be given as to how this information is placed in the public domain. The article can simply state the facts without any position being taken by MNF.
21.2.5 | BLP update | MM | 2021-03-31 | Closed | From an update provided via MCS, it is understood that the Inspector will be proposing Main Modifications to RBWM and there may be further consultation. Indeed RBWM is anxious for the inspection to be concluded and the BLPSV-PC approved.
21.2.6 | Funding | AI/IR/BB | 2021-03-31 | Closed | Secretary advised the meeting that the current funding lasts until end of March 2021, any planned expenditure needs to be before that date as unused funds have to be returned to Locality/Groundwork.
21.2.7 | Ascot and the Sunnings Neighbourhood Plan | AI | 2021-03-17 | Pending | Andrew has had an informal chat with Charles Appleby from the Ascot and the Sunnings Neighbourhood Forum. He has offered to brief MNF on his experiences. Agreed to follow this offer up.
21.2.8 | Draft Constitution for a federated MNF | AI/IR/AW | 2021-03-17 | Closed | AI and IR to review Feb-21 draft Consitution provided by AW
Item No. | Management Committee zoom meeting 17 Mar 2021 | Responsibility | Due date | Status | Commentary
Note: After item 21.1.2 this meeting was rescheduled to 18 March due to technical difficulties with Zoom
| Present |  |  |  | AI, IR, BB, JL, DD, AW, MM, MF, RD
21.3.1 | Progress with RBWM | AI/IR | 2021-03-31 | Closed | Letter to the Conservative Councillors has evoked a response from Cllr. Jones, suggesting the delay in arranging a meeting was due to pressure of work. Subsquent to receiving this response Andrew has received an email from Adrien Waite offering to meet but no date has been forthcoming. Andrew is actively pursuing the Head of Planning to secure a meeting.
21.3.2 | Presentation to Maidenhead Town Forum | AI/AR | 2021-03-31 | Closed | Following discussions with Cllr Taylor, the Chair (Cllr. David Coppinger), has agree to MNF making a presentation about our activities at the next meeting of the Town Forum to be held on 31 March 2021 by Zoom.
21.3.3 | Unspent funds (Locality Grant) | BB/AW | 2021-03-31 | Closed | As noted in Minutes 21.2.6, any unspent funds have to be returned to Locality at the end of the Financial Year. Ian circulated a list of collated suggestions as to how the fund could be used, see below. In the event due to the lack of progress with RBWM on designation it was felt premature to progress with any. The most useful would have been to secure a meeting room for use once we are clear of the pandemic, to allow face to face meetings to resume. However helpful this may have been, most venues currently are closed and there is uncertainty as to the arrangements for reopening, there was a preference to continue with zoom meetings. It was felt that we should try to use zoom for a wider participation by the Forum members. a) Buy a GIS mapping tool b) Book meeting venues to use once pandemic restrictions have been lifted c) Paying for Facebook 'boosts' d) Printing publicity leaflets e) Placing and advert in the Maidenhead Advertiser Mark asked about securing a Technical Support Package from Locality to assist with defining the activity of the Forum. Andy W. confirmed that TS packages were still available particularly once we are designated.
21.3.4 | AGM Date | AW | 2021-04-16 | Closed | Date to be confirmed, suggested that the meeting should be as late as possible to allow for some progress with RBWM to be made. Andy W. to suggest dates to discuss at the next meeting.
21.3.5 | Potential Policy Areas for MNF | IR | TBC | Pending | Ian tabled several areas which could form the basis of a draft NP, whilst provoking much discussion, the following areas were all agreed as being candidates for inclusion: > Local Green Spaces > Built Heritage > Green Corridors > Transport links > Design Codes > Development of the suburbs > Housing Mix and type > Waterway corridor > Access to Green Spaces > Ring Road barrier The main focus being to provide local detail which is not included in the BLP.
21.3.6 | NPPF Consultation | IR | 2021-03-27 | Closed | Richard and Andrew provided comments to Ian, response to be submitted on behalf of MNF
21.3.7 | Redevelopment of the former Magnet Site | JL | 2021-03-18 | Closed | Judith raised the issue of the proposed redvelopment of the Magnet site. Images which have been seen from the Planning Application, show very stark unattractive exteriors and tall buildings overlooking the adjacent list buildings. Whilst the concerns are noted and understood we have previously agreed not to comment on these schemes other than to post a link on the website. MCS is taking the lead in commenting on the scheme.
21.3.8 | Regeneration of Maidenhead Town Centre | RD | 2021-05-31 | Closed | Richard advised the meeting of the proposal by the 'Regen' group to revitalise the PRoM group. This proposal is finding some support in RBWM. Hopefully if it goes ahead MNF will be included as a stakeholder. Update 21/04/21 - the 'Town Team' proposal for submission to full council has been deferred until May.
Item No. | Management Committee zoom meeting 21 April 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, JL, DD, AW, MM, RD. Apologies: MF
21.4.1 | Progress with RBWM | AI/IR | 2021-05-07 | Closed | Since the last Management Committee meeting MNF was invited to make a presentation to the Town Froum by its Chair Cllr Coppinger. The presentation by Ian was well received and garnered some interest from members of the Forum (all Councillors). AI/IR/AW also has a zoom meeting with Cllr Coppinger and Adrien Waite on 17 April. Apologies were offered for the delay in meeting us, lack of staff within the Planning Dept being the main reason cited. Two further dates were proposed by RBWM and invitations received for 07 May and 04 June. During the call Cllr. Coppinger advised us that the proposal to create a new 'Town Team' has been deferred to the May council meeting.
21.4.2 | Proposed AGM date and schedule | AW | 2021-06-16 | Closed | The proposed dates for the AGM schedule were accepted - AGM to be held on Wednesday 30 June (to allow for full feed back from meetings with RBWM). - Notice to call the AGM to be issued on 16 June 2021 - As a consequence, the June MC meeting will be brought forward from 23 June to 09 June at the same time by zoom. Members suggested that the AGM and Full Forum meeting should be held at a later time (1900) to allow people who are working to participate. It was also agreed that there will need to be a campaign to encourage attendance as the meeting needs to be quorate (21 members present).
21.4.3 | Maidenhead Civic Society - membership offer | MM | 2021-05-19 | Closed | Martin outlined a proposal from Maidenhead Civic Soceity (MCS), to offer a year's free membership of MCS to all MNF members. Noting that a number of members are already members of both organisations. Agreed that this was a good idea and that the civic minded organisations should be encouraged to work together
21.4.4 | Maidenhead Climate Emergency Coalition | AI | 2021-05-19 | Closed | MNF has been appraoched by the Maidenhead Climate Emergency Coalition (CEC), to become formal members of the CEC. It was agreed that whilst we share some common objectives, there may also be areas of conflict and signing up to the CEC may put MNF in a difficult position. MNF would be happy to work jointly on specific topics and AI will attend the Areli/Nicholsons focus group. Action: AI to advise CEC. MM advised the meeting that the first planning application (development on Braywick Road), had been refused on the grounds that it did not comply with the requirements of the local Air Quality Management Area (AQMA). The existance of an AQMA in the local area was not previously known.
21.4.5 | RBWM Infrastructure Delivery Plan (IDP) | RD/IR | 2021-09-15 | Pending | Richard has prepared a summary of key issues in the revised RBWM Infrastructure Delivery Plan. Agreed to defer to next meeting to allow time for members to read the full IDP and comment on the summary.
21.4.6 | AOB | Note | 2021-04-21 | Closed | During the meeting some online reseach of Facebook, revealed that of our followers 59% are shown as female, 39% male and 2% not listed.
Item No. | Management Committee zoom meeting 19 May 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, DD, MF, RD - Apologies: MM, AW, BB
21.5.1 | Agenda for AGM | IR/AW | 2021-06-15 | Closed | The following items are needed for the AGM: - Calling notice and agenda - Chair's report - Annual financial report, checked by an independent person - Minutes/statement of the last AGM (in some form) - Appointment of Management Committee officers and members - Any other items we wish to present (what N. Plan can and can't do?)
21.5.2 | RBWM Infrastructure Delivery Plan (IDP) | AI/DD/RD | 2021-09-15 | Closed | Agreed that summaries of the IDP key section would be valued by members and others. AI and DD to draft one-page summaries for circulation (AI Education; DD Transport). RD to monitor any changes in the source document.
21.5.3 | Status of discussions with RBWM & Locality | AI/IR/AW | 2021-05-21 | Closed | Adrien Waite, Head of Planning, will be off work for "some weeks" for illness. We decided to continue with the scheduled meeting anyway, and include his two officer deputies Ian Moteul and Sian Saadeh.
21.5.4 | MNF procedure in post-lockdown world | AW |  |  | Pended due to absence of AW
Item No. | Management Committee zoom meeting 9 Jun 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, DD, RD, MM, AW, BB
21.6.1 | Status of discussions with RBWM | AI/IR | TBC | Closed | No progress to report since the meeting on 21 May. Adrien Waite remains on sick leave and to date we have not been advised of any deputising arrangements to cover the role in his absence. AI to follow up with Cllr Coppinger.
21.6.2 | Advice from Locality concerning designation | AI/IR | 2021-09-01 | Closed | Locality's advisor supporting MNF (Dave Chetwyn) recommends that we should separate the request for designation into Area and Forum. The logic being that the LPA cannot refuse to designate an area, it can only propose an amended area. Once this step has been achieved the Forum can be aligned to the designated area. The suggestion being that we should subject the existing area (with any changes we wish to make) soon after our AGM.
21.6.3 | AGM preparations | AI/IR | 2021-06-15 | Closed | AGM date: Following a diary conflict Ian has asked that we bring the date forward by a day to 29 June commencing at 1930 for 1 hour. This change of date was agreed. Calling notice to be amended and papers issued a day earlier. Management Committee 21/22: DD has advised the he is stepping down from the Committee. AW will be resigning as Secretary from the AGM, however will continue on the MC. AI/IR/BB/RD/MM and MF all agreed to continue in their roles. Sue Ingram has expessed an interest in taking over the role of Secretary - AW to assist with handover arrangements. IR has approached Deborah Mason to join the MC, with a favourable response. Calling notice and papers: Agreed that the Chairs' report would benefit from being in a presentation form and that it should list the MC members and record changes during the year. Financial report: Agreed that this should be kept as simple as possible due to the low level of financial activity Voting: Agreed that this should be by a show of hands on zoom. Voting in advance by e-mail if unable to attend the AGM, and requesting the Chair to act as proxy, will also be allowed in accordance with the Constitution.
21.6.4 | AOB | RD |  | Closed | RD advised the meeting thet the RBWM Vision and Charter paper was agreed at the 27 May Council Meeting, this enables the 'Town Team' to be created. Whilst it is useful to have a body providing focus, it appears to have no budget or authority so may be of limited effect on the development of the town. Members invited to join the 'Town Team' have not yet been announced.
21.6.5 | Locality Grant Funding | AW/BB | 2021-07-21 | Closed | AW advised the meeting that the application process for grant funding has just been opened by Locality. AW to find details from Locality as to what funding may be available, on the basis that for last FY only a minimal grant was awarded to MNF to assist with the designation process.
| Date of next Management Committee Meeting |  | 2021-07-21 |  | 1700 - 1800
| Date of AGM |  | 2021-06-29 |  | By Zoom at 1930
| Management Committee zoom meeting 28 Jul 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI,IR, MM, SI, BB, AW, RD, MF, apologies DM
Admin
21.7.1 | Sec Handover | SI/AI | 1.8.21 | Closed | AI to speak to MS about Sec @MNF emails (completed)
21.7.2 | Locality Grant | IR,AI, BB | 18.8.21 | Closed | BB to progress, Write simple Budget and apply for interim support pre-designation. AI, IR, BB to work together to apply
21.7.3 | Draft Designation Application progress | IR | 8.8.21 | Closed | IR to consult with Dave Chetwin for locality guidance, submission of pre-draft by 11.8.21. IR to 'Beef up' executive summary at beginning, then body, with fine detail of app'n to be in appendices. AI to circulate key facilities/ward instructions, to be completed by MNF committee by 8.8
21.7.4 | Draft RBWM BLP, Summary of main modifications | IR | 1.9.21 | Closed | MNF will submit a short summary, 1 page response written by IR. Minor tweaks to BLP but nothing significant for MNF to comment on. MNF welcomes protection of heritage assets and blue infrastructure. Welcomes specific endorsements of waterways projects. IR to include comments about lack of any 'masterplan' for new developemnt, in line with inspector's observations and RD feedback 18.8.21
21.7.5 | Spencer’s Farm, Summary of consultation 22 July | MM | 29.7.21 | Closed | No specific actions at the moment, MM to attend update 29.7.21, report back if any new items. Possible future MNF input in design code of new plans as they develop.
21.7.6 | Timings of Mgmt Mtgs | IR | 28.7.21 | Closed | 3rd Weds every month, 7pm, plan for 1 hour, on Zoom till designation
| AOB |  |  |  | none
| Date of next Management Committee Meeting |  | 2021-08-18 |  | 1900 - 2000
| Management Committee zoom meeting 18 Aug 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, IR, BB, SI, RD apologies MM, AW
21.8.1 | Locality Grant progress to date | AI, IR | 1.9.21 | Closed | BB has completed spreadsheet, AI & IR to assist with application. Post-area designation we will need Software is £1500 (ongoing cost), as per MF suggestion
21.8.2 | New Locality Grant appn | BB | 1.9.21 | Closed | BB to apply for small £400 Funding grant from 21-22 budget for incidental costs we may incur prior to designation
21.8.3 | Draft Designation Application- progress | IR | 1.9.21 | Closed | All MNF committee are happy with suggested app'n. Inclusion of table in annexe, and reference to annexe from main text. Doc was sent to Dave Chetwyn 20.9.21
21.8.4 | Local facilities per ward, annexe summary | IR | 1.9.21 | Closed | Summary table will be inserted as annexe E, and referenced from main text
21.8.5 | Status of actions MNF response to draft BLP | IR | 15.9.21 | Closed | Brief positive response to BLP, before 15th Sept. No progress on setting up Town Team to date. Support idea of Town Centre Masterplan and Supplementary Planning document.
21.8.6 | Status of all actions discussed | IR, AI | 1.9.21 | Closed | All previous 'open' actions were discussed, some are now pending, and some have been closed. IR and AI to discuss Estate agent and the Civic Society response to MM
21.8.7 | AOB - Climate consultation | AI | 18.8.21 | Closed | Not within Remit of MNF so no further action to be taken by MNF
21.8.8 | AOB - Active travel consultation | AI | 15.9.21 | Closed | AI to check questinnaires,
| Date of next Management Committee Meeting |  | 2021-09-15 |  | 1900 - 2000
| Management Committee zoom meeting 22 Sep 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, SI, RD, DM, IR, MF, BB, Apologies MM AW
21.9.1 | Locality grant application progress update | BB | 7.10.21 | Closed | Grant has been awarded, Bank details & due diligence to be completed
21.9.2 | Draft designation application; Executive summary progress to date | IR | TBC | Closed | Pre-app'n designation submitted to DC who recommended reduction of document, and he asked for appendices to be removed; Cut-down version sent to RBWM on 20-Sep-21. Requested mtg with locality and DC. IR to advise MNF when we get a date and what has finally been submitted. N.B. RBWM are allowed 13 weeks to process formal app'n
21.9.3 | MNF’s response to draft BLP | IR |  | Closed | MNF has submitted positive response to draft BLP on items that we were allowed to comment on-
21.9.4 | Active Travel Consultation progress | AI | 30.09.21 | Closed | MNF member to attend 29.9. AI advised MNF not to complete flawed questionnaire
21.9.5 | Infrastucture Delivery Plan IDP | DM, AI | 20.10.21 | Closed | 17.11.21, Updated commentary (see notes below at Nov 21 mgmt mtg,) Ai to contact DM to ask for documents to be emailed. DM will provide timetable of event moments plus text & will stagger release of documents and IDP data to all MNF members & social media. AI to write article for Maidenhead Advertiser. 20-Oct-21: AI to e-mail DM to complete timetable of event moments and text.
21.9.6 | Locality Grant for Mapping software | MF |  | Pending | Post-designation we will need Software £1500 (ongoing cost), as per MF suggestion (see 21.8.1)
21.9.7 | Status of actions from previous meetings | IR |  | Closed | All open actions reviewed, some closed, some amended.
| Date of next Management Committee Meeting |  | 2021-10-20 |  | 1900-2000
| Management Committee zoom meeting 20 Oct 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, SI, RD, IR, MM, MF, AW, BB Apologies DM
21.10.1 | Locality grant application progress update | IR, BB, MM | 17.11.21 | Closed | Money rec'd but needs clarification . We are unincorporated body but Locality requires funding to be made to an incorporated body - ie Civic Society. Protocol needs to be set up. We need to arrange mtg with Peter Childs, plus IR, BB, MM, as MNF representatives
21.10.2 | Draft designation application; Executive summary progress to date (IR) | IR | 17.11.21 | Closed | We are still awaiting response to our application. AW has delegated task to senior officer.
21.10.3 | Status of actions from previous meetings , (including active travel consultation) (IR) | IR |  | Closed | All open actions were reviewed, some closed, 21.9.5 commentary amended.
21.10.4 | COPtober | AI |  | Closed | No Action
21.10.5 | AOB - Gas Boilers in Magnet Site | AI | 29.11.21 | Closed | AI to draft letter to AJ Lead Council to ask Borough (as joint venture partner with new developments) to lead by example re green eco construction in Borough. IR send as Chair MNF. Copy in David Coppinger, Donna Stimson
| Date of next Management Committee Meeting |  | 2021-11-17 |  | 18.30-19.30
| Management Committee zoom meeting 17 Nov 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, SI, BB, MM, AW, IR,RD, MF. Apologies DM
21.11.1 | Locality grant application progress update | BB | 15.12.21 | Closed | Awaiting confirmation & clarification of protocol from Groundworks & Peter Childs, Grant has already been rec'd.
21.11.2 | Draft designation application; Progress to date | IR | 15.12.21 | Closed | Still awaiting response from AW and team
21.11.3 | Infrastructure Delivery Plan IDP | AI | 15.12.21 | Closed | further to 21.9.5 (above) AI will notify local people that there IS an IDP and relevant topics; Plan release day, give advance notification to allow people to 'like' and 'comment' on social media to provoke discussion, and send press releases to Maidenhead Advertiser
21.11.4 | Gas Boilers in Magnet Site – Progress to date | AI |  | closed | No progress to date, item closed.
21.11.5 | Mapping - comments | All | 15.12.21 | open | Further to MF map info from other nearby boroughs, all Committee members to review what is available on existing Royal Borough Mapping tools, (My Neighbourhood Map) explore opportunities and value of such maps, then report back before next meeting
| Date of next Management Committee Meeting |  | 2021-12-15 |  | 19.00 - 20.00
| Management Committee zoom meeting 15 Dec 2021 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, SI, MM, IR, BB, RD, AW
21.12.01 | Locality grant application progress update | BB, RD | 19.01.22 | Closed | BB to call Peter at Civic Society to sign off this year; if OK AI/IR will sign latest version of protocol and pass on to Bob Dulson. RD will ask trustees if they can use Waterways as accountable body next year.
21.12.02 | Draft designation application; Progress to date | AI | 19.01.22 | Closed | Option B: Survey MNF followers, listen to views, then take next steps dependent on responses. Request discussion with Borough and Dave Chetwyn. AI to create survey asap and then provide press release about MNF, Survey and in Borough newsletter. Results by next meeting
21.12.03 | Infrastructure Delivery Plan IDP | AI | 24.12.21 | Closed | Once summary of IDP is published Mai Advertiser, AI will follow up with social media posts. (We need to remind people that are not endorsing plans). AI will notify David Coppinger as courtesy
| Date of next Management Committee Meeting |  | 2022-01-19 |  | 19.00 - 20.00
| Management Committee zoom meeting 19th Jan 2022 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI,SI,IR, RD,BB, MF, MM Apologies AW
22.01.01 | Locality grant application progress – update | BB | 19.01.22 | Closed | Waterways group (as accountable body) have offerd to receive grants on behalf of MNF in future applications
22.01.02 | MNF IT infrastructure | AI | 31.1.22 | Closed | Following recent hack, MNF Webside is still there, but has been rebuilt and simplified by AI, and has been migrated to be hosted by MS Server (thank you Matthew). Officers' emails need to be remotely altered by Mark Osborne from POP to IMAP. AI to ask MO normal hourly rate and how many hours this has taken and request invoice. AI also suggested using some grant money to pay £10 pa for each email a/c for storage for officers & any additional active email addresses . Review other email addresses, migrate active ones or close down inactive email addresses.
22.01.03 | Draft designation application; Progress to date and comments from recent publications, responses to media | IR | 16.2.22 | Closed | No progress to date, Survey is on hold following website hack. No more responses from Planning dept as formal application has not yet been sumbitted. No new actions following on from Town Forum meeting. Mai. Advertiser article 13th Jan was reported factually and all published information was in public domain. RBWM officer Ian Manketelow agreed to have discussion with MNF after area survey results were available.
22.01.04 | Designation Area survey results | AI, IR | 02.02.22 | Closed | 126 responses to date before website crashed. AI to restart survey for those people who weren't able to contribute previously and set new deadline one week. AI to speak to MS about loading survey onto new MNF website. AI to appeal for more responders via Mai Advertiser, Facebook and other social media. Once deadline is reached and survey is closed, IR to interpret survey data results and create graphs/pie charts
22.01.05 | Develop closer working relationship between Maidenhead Civic Society & MNF | AI, IR | 16.02.22 | Closed | MM passed on message from CS who want to work more closely with MNF. AI & IR to speak to Civic Society
| Date of next (extra) Management Committee Meeting |  | 03.02.22 |  | to discuss outcome of survey
| Management committee zoom meeting 3rd Feb 2022 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, SI, IR, RD, MF, BB, Apologies AW, MM
22.02.01 | Designation Area survey results | AI | 06.02.22 | closed | 138 completed surveys, targeted on people who have an interest on M'head. Approx 60% response rate. AI to tweak doc based on feedback from MNF members.
22.02.02 |  | IR | 06.02.22 | Closed | Reply to Dave Chetwyn & inform him of the status, including draft survey results document
22.02.03 |  | IR | 07.02.22 | Closed | Send the survey results document to RBWM & request meeting Adrien Waite, I Manketelow, Dave Chetwyn
22.02.04 |  | IR | 16.02.22 | Closed | Prepare area resumbission application to RBWM, revised MNF application, and include survey results, list of members, constitution & other supporting documents
22.02.05 |  | AI | 15.02.22 | Closed | Write press release & submit survey results, map, chart, to Advertiser for publication 17th Feb, and social media Facebook etc after press day.
| Date of next (Normal) Management Committee Meeting |  | 16.02.2022
| Present |  |  |  | AI, SI, IR, MM, RD, AW, MF - apologies BB
22.02.06 | Draft designation application; Progress to date. | IR, AI, MM | 23.02.22 | Closed | IR to modify designation application, AI & MM to supply membership list; then request mtg IR/AI, Adrien Waite, Ian Manktelow
22.02.07 | Designation Area survey results – status of follow-up actions | AI, IR |  | closed | follow up actions completed
22.02.08 | Develop closer working relationship between Maidenhead Civic Society & MNF – mtg planned for 22nd Feb | IR, AI, MM | 22.02.22 | Closed | Meeeting planned 6pm 22nd to be attended by MM, IR, AI
| Date of next Management Committee Meeting |  | 16.03.2022 | 7pm
| Management Committee Zoom meeting 16th March 2022 | Responsibility | Due date | Status | Commentary
| Present |  |  |  | AI, SI, IR, RD, MF, BB, AW Apologies MM
22.03.01 | Draft designation application; Progress to date. | AI, IR | 30.03.22 | Closed | Meeting with RBWM on 10-Mar-22 was generally positive and clarified many issues. Formal RBWM feedback on MNF's draft Area application due 31-Mar. IR & AI to look at Locality Roadmap guidance on the requirements for Forum membership and obtaining a more diverse membership. Currently awaiting feedback from RBMW and then plan next stage of process
22.03.02 | Follow up from MNF and Civic Society meeting on 22nd Feb | AI, IR, MM | 22.03.22 | Closed | Attend next meeting scheduled 22 March. The MNF consensus view is not to merge MNF and MCS into one group.
22.03.03 | Update of membership database | AI, SI, IR, AW | 20.04.22 | Closed | Defer to next meeting The current .csv file of membership data is missing some data that is required to show the Forum is capable of being deisgnated. The information has been obtained, but the database needs to be updated. May need to liaise with Matthew Shaw.
22.03.04 | Review of Data protection policy | AI, IR, SI, RD | 20.04.22 | Closed | Defer to next meeting Useful input in e-mails from SI and RD provided before 16-Mar meeting.
22.03.05 | Can new members join using the current website? | AI, IR | 20.04.22 | Closed | Defer to next meeting The website currently asks members to e-mail chair@mnf.org with details, but the details are a subset of those collected previously and omit for example age. The extra data is needed to check diversity.
22.03.06 | Help to set up editor@mnf.org on Microsoft Outlook | IR | 23.03.22 | Closed | Ian to speak to Mark Osborne IT expert from Cavalry Computers
22.03.07 | Possible purchase of Microsoft Visio for creating diagrams | IR | 23.03.22 | Closed | Unanimous approval by committee for one-time purchase to be downloaded onto IR personal computer.
22.03.08 | AGM in June | AI | 18.03.22 | Closed | Book hybrid AGM meeting at Bowls club 27-30th June?
22.03.09 | SW M'Head meeting March/April | All | 29.03.22 | Closed | Delegates to attend & share feed back to group at next MNF committee mtg RBWM sessions are 30-Mar, 6-Apr and 13-Apr, all online only.
| Date of next Management Committee Meeting |  | 27.04.22 | 5pm
| Mangement committee Zoom meeting 27th April 2022 | Responsibility | Due date | Status
| Present |  |  |  | AI, SI, MM, IR, AW, MF, RD, BB
22.04.01 | Draft designation application; Progress to date. | IR | 18.05.22 | Closed | Ian R has heard from Ian Manketlow- now MNF awaiting more feedback post- RBWM meeting which is this week 25-29 Apr.
22.04.02 | Finances (account status, '23 Budget, '23 grant app'n) | BB, IR, AI, RD | 18.05.22 | Closed | Bob B has requested input from group what grant money we need. Cannot yet apply for Grant. (app'n process not yet open). MNF agreed to accept Trustees of Maidenhead Waterways kind offer to act as the accountable body for MNF (Mark Loader is Treasurer, needs to apply for the Locality grant on our behalf)
22.04.03 | Plans for AGM in June | IR, AI | 18.05.22 | Closed | Room booked at DBC 7th June for factfinding about MNF for those who expressed interest, invite Suzie Shearer from Windsor Neighbourhood Plan, and recruit Treasurer. (AW willing to step in short term till) AGM booked 27th June. Factfinding meeting should include candidate policy areas identified so far by MNF.
22.04.04 | Update on plans for meeting with Phil Haseler | AI | TBC | Closed | AI compiled list of of topics, invited PH to discuss, and is waiting to hear back from PH re meeting
22.04.05 | Update of membership database | AI, IR, SI, RD | 18.5.22 | Closed | Mtg to be held with Matthew Shaw, as database needs tidying up. Review Mailchimp. And ensure Data Protection Policy is adhered to.
22.04.06 | Can new members join using the current website? | AI | 18.05.22 | Closed | Yes, but system needs to be automated following discussion with MS
22.04.07 | Feedback from SW M'Head meetings March/April |  |  | Closed | MNF decided not to make any input to the SW M'Head SPD. MNF has informally discussed RBWM's SPD consultation sessions with Maidenhead Great Park and with Wild Maidenhead.
22.04.08 | Follow up from MNF and Civic Society meeting | AI |  | Closed | Merging not feasable. Led to need to follow up with Phil Hasler (item 04)
22.04.09 | Review of Data protection policy |  |  |  | Refer to item 5 above
| Date of next Management Committee Meeting |  | 18.05.22 | 7pm
Management committee Zoom meeting 18th May 2022
| Present |  |  |  | AI, SI, IR, BB, MM, MF, RD
22.05.01 | Draft designation application; Progress to date and feedback from Ian Manketlow |  | 12.06.22 | Closed | RBWM Ian Manktelow had responded 10-May, key points being evidence for community support for the Area, and Forum designation requirements to be met in full even at Area designaton stage. IR sent reply email on 16th May, now awaiting response from Ian Manktelow re f2f meeting date.
22.05.02 | Finances – (Status of 2023 grant, is app'n process open yet? Maidenhead Waterways as accountable body) | BB, FoMW, IR, AI, RD | 31.05.22 | Closed | Approval given for MW as accountable body name of Maidenhead Waterways Restoration Group, go ahead to sign latest update of protocol. Locality App'n system is now open, BB has completed draft app'n; IR & AI to check. AI and RD will work with BB to include budget for more publicity items. Then BB to submit naming MWRG as accountable body.
22.05.03 | Plans for MNF Factfinding event DBC 7pm on 7th June | AI | 21.05.22 | Closed | AI to redraft agenda, and extend invitation to other groups. We intend to expand numbers who are actively engaged to a wider membership, and attempt to recruit treasurer at 7th June mtg.
22.05.04 | Plans for AGM 27th June | AI | 12.06.22 | Closed | As 14 days notice for AGM needed, invitation must be sent out by 12 June. AI to cancel DBC as it will be a Zoom meeting. Officers to finalise AGM details prior to 12.06.22. IR to find person willing to examine accounts, Richard Curry has been approached.
22.05.05 | Any news on meeting with Phil Haseler? | AI | TBC | Closed | NO
22.05.06 | Progress to date - membership database & MNF website | AI, IR, SI | TBC | Closed | AI has reviewed website which now contains new member signup form and collects required data. Progress made with database and link re-established between MNF website and Mailchimp database. Mailchimp database needs edit to update missing/wrong data; Data Protection policy to be reviewed in due course.
22.05.07 | Update status of actions | IR, SI | 21.05.22 | Closed | to follow
| Date of next Management committee meeting |  | 15th June | 7pm
Management committee Zoom Meeting 15th June 2022
| Present |  |  |  | AI, SI, IR, MM, BB, MF, RD apologies AW
22.06.01 | Draft designation application; Progress to date | IR | 17.06 | Closed | IR to send draft documents to RBMW Hybrid meeting 30th June, Borough to provide documents ahead of mtg listing groups they want us to engage with. Attendance expected by Dave Chetwyn (Locality), Ian Manktelow (RBWM), Ian Motuel (RBWM)
22.06.02 | Finances and status of 2022/23 grant | BB |  | Open | App'n for £5499 grant sumbitted, awaiting response.
22.06.03 | Plans for AGM 27th June | BB, IR, AI, SI | 19.06 | Closed | BB is awaiting signed examiner's report from Richard Curry and RC to add paragraph to financial report . Minor amendments to be made to draft Chairs' report and will be submitted by 20th (1 week prior to AGM). AI & IR to approach potential new members for Management committee & especially new Treasurer. No Quorum is specified for the AGM, but only members may vote. Sue to send out minutes of previous AGM, plus Chairs' report, Financial Report and zoom link by Monday 20th June.
22.06.04 | MNF Factfinding event 7th June |  |  | Closed | Bill paid for Des. Bowling Club for mtg using existing funds & donations. Follow-up documents have been sent out. No further actions required.
22.06.05 | Update on plans for meeting with Phil Haseler | AI | 19.06 | Closed | AI to draft letter & keep an informal relationship with PH, but we no longer plan to hold Q&A session as previously suggested.
22.06.06 | Membership database & MNF website | AI | 19.06 | Closed | In hand, AI working on improvements
| Date of AGM 27th June 2022 |  | 27th June
| Date of next Management committee meeting |  | 20th July
Management Committee Zoom Meeting 20th July 2022
| Present |  |  |  | AI, IR, AW, PM, PA, RD, MF, Apologies SI, MM. Welcome Pam and Phil
22.07.01 | Feedback from AGM |  |  | Closed | There was support for pursuing designation for area AND forum now (because of RBWM view that "Forum capable of being designated" test for Area application is the same as the full Forum application test)
22.07.02 | Feedback on meeting with RBWM re Draft designation application; Progress to date | IR | 28.07.22 | Closed | Very positive mtg. More diversity is required, Cllr Haseler suggested FAQ for outreach project. Dave Chetwyn says RBWM are applying criteria too strictly for designation stage. IR to draft Forum Designation Request.
22.07.03 | Update on progress made in trying to reach more diverse groups | ALL | 28.07.22, draft 1st e-mail earlier | Closed | We now have contact info for diverse groups and list recommended by RBWM team. AI to draft first email/letter of contact. Mgmt Cttee will take 1 or 2 each. •Sue – WI, Soroptimists • Andrew – Rabbi • Phil Adkins – Maidenhead Nomads (young football team) • Andy W – Bahais • Mark – Gurdwara, Mosque, Taweed • Pam – Disability & Inclusion Forum, Ladies Circle • Ian – Hindus • Richard – Chamber of Commerce
22.07.04 | Finances and status of 2022/23 grant application | PA | 28.07.22 | Open | Phil is expecting £5000+ funds to be paid into MNF account, but it should be paid to FoMW as accountable body. Clarification needed.
22.07.05 | Update on letter to Phil Haseler | AI | 28.07.22 | Closed | Andrew seeing him on 28th but unlikely to produce a Planning step forward
22.07.06 | Membership database & MNF website | AI, RD, PM | 28.07.22 | Open | AI no great movement on membership (no stimulus) but planning to promote South West Mhd SPD opportunity on website and F'bk. - MNF website sign-up procedure: selected age group changes over time; agreed to ask for Year of Birth not Decade of birth Gender should be at top of list (RD, AI to change) “Organisation” box should be clearer (AI to change) - MNF Website: Not good on mobiles (PM, AI to investigate) MNF status is "not yet designated", AI to clarify - Privacy Statement, RD to check - AI: send link to SWM SPD to members
22.07.07 | RBWM South-West Maidenhead consultation - | AI | 26.07.22 last open session | Closed | Plans available in Library, AI to circulate. Summary on Website. A308 may become strategic Road, Highways funding?
| AOB |  |  | Closed | Duncan Sharkey RBWM CEO has resigned, His replacement & impact on RBWM and MNF Unknown. Town Team now likely to be re-thought by Cllr Coppinger
| Date of next Management Committee Meeting |  | 17th August
Management Committee Zoom Meeting 17th August 2022
| Present |  |  |  | IR, AI, SI, AW, RD Apologies MM, PA, PM
22.08.01 | Feedback on meeting with RBWM re Draft designation application; Progress to date | IR. AI, | 1.9.22 | Closed | Draft forum app'n was sent to Dave Chetwyn who is happy with it as diversity levels ok. Next, IR to re-draft designation application; progress made with latest contact list (AI) plus noticication about updated constitution also to be sent to Ian Manktelow at RBWM,
22.08.02 | Update on progress made in trying to reach more diverse groups | AI | 1.9.22 | Closed | Progress has been made; AI to provide summary of progress of new contacts to IR, based on RBWM contacts list, > ready to sumbit to RBWM
22.08.03 | Finances and status of 2022/23 grant application |  | 21.9.22 | Closed | Status of grant not currently known, RD reported that it had not reached Maidenhead Waterways account.
22.08.04 | Requirement to amend constitution | SI, AW, IR | 31.08.22 | Closed | SI to check handover docs, confirm with AW that it is latest version, then forward to IR. IR to redraft constitution re membership, (Remote meetings option also to be added to revised constitution) share with Locality Dave Chetwyn and Management committee, then 7 days notice is required for EGM, ie By 31st August for 7th Sept target for EGM. Expect to run EGM as remore meeting and to allow remote voting prior to meeting, note quorum requirement of 1/3 members.
22.08.05 | Membership database & MNF website | AI, IR, SI | 23.8.22 | Closed | More members have recently joined. Website joining form needs new tick box for privacy policy (AI). IR to bring hard copy of Updated Privacy Policy for co-chair and secretary signatures and then uploaded onto website.(IR, AI). Membership details need updating with further gender and ethnicity boxes. SI, AI to check if can be done at same time as accepting revised Constitution using voting buttons on email.
22.08.06 | RBWM South-West Maidenhead consultation - |  |  | Closed | SPD closing date 17th Aug, MNF Mgmt Committee decided not to contest. No further action from MNF
SGM was held on Wedsnesday 7th September
Management committee Zoom Meeting 19th October
| Present |  |  |  | AI, SI, IR, MM, AW , RD, MF, PM
22.10.01 | Update on progress on MNF designation application | IR | 26.10.22 | Closed | Ian Manktelow has asdvised that consultation will be starting 25.10.22, is expected to last 6 weeks and end on 6th Dec; Decision expected by Christmas. We need to promote locally. See item below..
22.10.02 | Plans to publicise to members & Maidenhead residents | All | 26.10.22 | Closed | RD to Map-out communication timescale for next 6 wks, Extra meeting set up 26th at 5pm; Suggestions include or Map, photos, promotion on Social Media; add to Borough newsletter; Maidenhead Advertiser articles, letters, features.
22.10.03 | Membership request by RBWM | AI | 20.10.22 | Closed | AI to send out email to all membership re consent for RBMW contact info as per RBWM designation request
22.10.04 | Finances and status of 2022/23 grant application | PI | 20.10.22 | Closed | No money rec'd yet. IR to contact PA re situation re grant & finances
22.10.05 | Membership database & MNF website | SI | 26.10.22 | Closed | SI to update database with latest changes
Extra meeting Weds 26th Oct 5pm
| Present |  |  |  | AI, SI, IR, AW, RD, MF apologies PM, PA, MM
22.10.06 | Vacancy for Treasurer | AI | 01.11.22 | Closed | Approach members and ask for someone to volunteer as treasurer, and track down grant which has been approve. Send out 2 days after 1st mailing sent to members re Designation
22.10.07 | Update on progress on MNF designation application | IR, AI | 28.10.22 | Closed | IR to write daft message, AI to email (mailchimp) members - explain of importance of responding to consultation doc for Maidenhead N'hood Forum with link to short video - AI to contact Gavin Ames re Viewpoint article. Required week 5..
22.10.08 (a) | Scope of engagement plan drafted by RD Week 1 | All | 01.11.22 | Closed | AI to notify FB with post about MNF consultation. Following that, MF to re-post on facebook groups with links to consultation document, including IR's 'How to' respond with screenshots. AI to sumbit article to Mai Ad; SI to notify PA & MM re group photo 9.30am Fri. MF to find out # neighbourhood plans in UK for article. AI to post on 'Next Door' website.
22.10.08 (b) | Write to councillors Week 2 | PM | 9.11.22 | Closed | IR to ask PM to write to all councillors, plus TM, as per RD article.
22.10.08 (c) | Email to Maid Advertiser - week 3 | AI | 16.11.22 | Closed | AI to write open letter to Advertiser erminding residents to respond to consultation
22.10.08 (d) | Chase email MNF members, week 3 | AI | 16.11.22 | Closed | AI to resend message to MNF members, reminding all to respond to consultation- revised header
22.10.09 | IR to thank Ian Manktelow | IR | 28.10.22 | Closed | IR to write to Ian Manktelow to thank for his activity so far. Ask for sight of responses if possible
22.10.10 | Review FAQ updated by Andy Woodcock | MF |  | Closed | MF to find exact rules for FAQ text on s106 and CIL - but otherwise all agreed to take Andy's version unless feedback from neighbours requires amendments
22.10.11 | Prepare list of materials to prepare | SI | 28.10.22 | Closed | SI to list documents required - as listed in minutes
Management committee zoom meeting 16th November 7pm
| Present |  |  |  | AI, SI, IR, MM, PM, AW,RD apologies from MF
22.11.01 | Update on progress on MNF designation application. | AI | 23.11.22 | Closed | All C'ttee members have had +ve feedback; Viewpoint article written; All MNF members have fulfilled their allocated tasks. Advertiser article & Membership nudge to follow next week.
22.11.02 | Finances and status of 2022/23 grant application | IR, RD, AW, AI | 23.11.22 | Closed | No grant yet rec'd. IR to ask Phil who he contacted, RD to ask locality . AW to contact his former contact, AI to progress treasurer inbox IT issue
22.11.03 | Vacancy for Treasurer |  |  | Closed | Pending, awaiting designation
22.11.04 | Membership database & MNF website | AI, SI, | 23.11.22 | Closed | AI & SI to clarify anomalies & clean up database
22.11.05 | Review actions from previous minutes & discuss which can now be closed. |  |  | Closed | All outstanding actions reviewed and many have been closed
22.11.06 | Engage with other wider ethnic group | AI | 23.11.22 | Closed | AI suggested we need relationship with WAMCF, also Follow up Chamber of Commerce & Mark Harris re consultation feedback to RBWM
22.11.07 | Feedbck from consultation | IR | 7.12.22 | Closed | IR to ask RBWM Ian Manktelow about designation responses received, and how they can be accessed
Management committee Zoom meeting 21 Dec , 7pm
| Present |  |  |  | AI, SI, IR, MM, RD apologies AW, MF, PM
22.12.01 | Grant update | All | 31.12.22 | Closed | Refresh budget with realistic projection of what we will most likely spend money by 31.3.23. Unspent money will need to be returned
22.12.02 | Designation application update |  |  | Closed | We have acccess to all 103 responses to consultation - Now awaiting outcome.
22.12.03 | Vacancy for treasurer |  | tbc | Closed | Pending, awaiting designation. If we get designated, include request for treasurer in the same publicity release.
22.12.04 | Potential for RBWM office support & Cash grants | IR | 11.01.23 | Closed | IR to investigate from David Chetwyn if we can expect any officer support/funding from Borough if/when we do get designation. Also consider asking RBWM planning directly.
22.12.05 | Next steps, assuming designation | All | 31.12.22 | Closed | 1- Prepare media announcement; 2- Prepare mailings (inc recruitment treasurer) & other literature; 3- Book large-scale public meeting for end-Jan; 4- Invite councillors ASAP to Zoom mtg with some of MNF Committee to inform them about MNF, & reassure them of our intention to help Maidenhead community, give Councillors opportunity to ask us questions which may help prepare their manifesto - and also invite them to subsequent Public meetings; 5- Hold a Public meeting in 3 parts: a) Explain MNF, Borough planning system & MNF limitations b) Get soundings and ideas and pubic input c) Recruit people willing to get involved
22.12.06 | Obtain previous programme from AW | IR | 11.01.23 | Closed
22.12.07 | Membership database and MNF Website |  |  | closed
F-F Management committee meeting 18th Jan 2023,7pm Ashbury House
| Present |  |  |  | AI, SI, IR, AW, MM, MF, PM, Mick Jarvis, RD on Zoom
Mick Jarvis welcomed as observer
23.01.01 a | Next steps, now we have designation | AI | 1.2.23 | Closed | Produce Survey & send to members, assess commitment, time, skills. Ask for Treasurer
23.01.01 b |  | AI/SI | 21.1.23 | Closed | Find venue for Forum members meeting, prob 22 Feb 23 ? Desborough Bowls Club or elsewhere
23.01.01 c |  | AI/SI | 21.1.23 | Closed | Find venue for Public meeting (29th March?) - larger capacity
23.01.01 d |  | IR | 15.2.23 | Closed | Produce draft Presentation for MNF forum meeting
23.01.01 e |  | IR & AW | 1.2.23 | Closed | Draw up plan of action and timetable for next phase of Forum activities
23.01.01 f |  | AI | 1.2.23 | Closed | Invite members to First F2F Forum Meeting
23.01.01 g |  | AI | 1.2.23 | Closed | Rough draft of banner and leaflets
23.01.01 h |  | AW | 1.2.23 | Closed | Andy Woodcock to get quote for local maps (laminated?)
23.01.01 i |  | PM? RD? | 1.2.23 | Closed | Get quote for cost of banners and printing leaflets
23.01.02 | Public meeting | AI | 15.2.23 | Closed | Invite Phil Haseler, Ian Manktelow, Andrew Durrant, Ian Motuel, forum members and Maidenhead Residents to Public meeting. Work on relationship with officers and prospective councillors
23.01.03 a | Financial update | All | 31.03.23 | Closed | Ensure as much grant is spent as possible on budgeted items prior to year end - when unspent money must be returned
23.01.03 b | Financial control | AW | 1.2.23 | Closed | AW to provide draft Financial controls document
23.01.04 | Andrew workload | AI | 1.2.23 | Closed | In initial survey, AI will request someone with relevant skills to offload some tasks currently done by Andrew - Wordpress, GIS Software, etc
23.01.05 | Treasurer vacancy | AI | 1.2.23 | Closed | as above, AI to write to members requesting specific skills - as treasurer
23.01.06 | Constitution update | IR, Treasurer | 31.5.23 | Closed | Constitution needs to be updated to align with Maidenhead Waterways as accountable body
Next MNF committee meeting 15th Feb 7pm (F-F?)
F-F management committee meeting 15th Feb Ashbury House
| Present |  |  |  | AI, SI, IR,AW, MF,RD,MJ Apologies MM
23.02.01 a | Plans for MNF Forum meeting 23 Feb | SI | 17.02.23 | Closed | Logistics - room layout, AV, Name Badges, refreshments, invoice
23.02.01 b | At Forum meeting | All | 23.02.23 | Closed | Presentation (Ian & Andrew); Way Forward - get consensus from Forum ; Q&A at end. Ask for Vounteers to help at Public meeting, and a Treasurer; Minutes (Sue) Update .ppt presentation to show one side for short term schedule and one slide for whole schedule (IR)
23.02.02 a | Preparation for Public meeting 30th March | SI, MF, AW, MJ | 01.03.23 | Closed | Logistics at DBC (Sue) Organise to get banners printed (?); Maps (MF) get printed (AW) . Source Gazebo (MJ)
23.02.02 b | Timetable | AW | 22.02.23 | Closed | Produce Gantt Chart with date/plan of action prep Public mtg with dates & deadlines for Mai Advertiser, Borough newsletter, etc
23.02.02 c | Maps | AW/MF | 14.03.23 | Closed | Maps: For 30th March meeting, Check copyright of MF's annotated map and quality of reproduction; Mark to produce PDF, Andy to send to print. Future: Mark to research Parish online maps or alternatives, ready for decision at 15-Mar meeting and subscribe/pay before 31st March
23.02.02 d | Facilitator | AI | 20.02.23 | Closed | Get facilitator for 30th March meeting; offer fee for advance preparation and for delivery on the day
23.02.02 e | Online input | AI | 14.03.23 | Closed | Opportunity for people not attending meeting to input ideas Direct people to MNF website, which will have contents of banner displays; FAQs including what is in BLP Website to contain online method of garnering ideas and suggestions Opportunities to contribute or ask questions instead of or before they come to meeting - email or post.
23.02.02 f | Invitations | AI | 14.03.23 | Closed | Invite Forum members residents to public meeting - Send invitations to all diversity and outreach stakeholder groups (Civic Soc, Mosque, Disability groups, Eco groups etc); RBWM councillors (existing and prospective), Phil Haseler, Ian Manktelow, Andrew Durrant, Ian Motuel
23.02.02 g | Publicity | AI | 14.3.23 | Closed | Article for Mai Advertiser, 23 Mar & 30 Mar. Also Borough Newsletter, publish in Facebook, Next Door? Other social media?
23.02.02 h | Roller banners | AI | 14.03.23 | Closed | Provide concept for 5 banners Allocate who provides actual material and arrange internal agreement
23.02.02 i | Presentation | IR | 14.03.23 | Closed | Provide presentation for first part of meeting Include how and when MNF will provide feedback on the ideas provided
23.02.03 | At Public meeting |  | 30.03.23 | Closed | Visitors to view banner displays on arrival and half time at meeting; Intro and talk at meeting; Display flipcharts around room for post-it comments and photograph all charts
23.02.04 | After Public Meeting | SI | 05.04.23 | Closed | Collate feedback from meetings & make available on website.
23.02.05 | Financial update | RD? |  | Closed | Mailchimp £40/month; AI to investigate payment schedule. Mapping software @ £750/pa; Maps £40, leaflets? Roller banners?
23.02.06 | Treasurer vacancy | All | 30.03.23 | Closed | Ask again at Forum Meeting
23.02.07 | Draft Schedule | AW | 20.02.23 | Closed | Spreadsheet to be revised and adjusted following discussions and amended in line with Rules & Regs. Regulation 14 consultation on pre-submission draft is actively run by MNF. AW to include line for regular dialogue with RBWM
Next Management committee 15th March, Ashbury House
Management committee meeting 15 March Ashbury House
| Present |  |  |  | AI, SI, IR, RD, MF, MJ, NS. AW Apologies MM
23.03.01 | Introduction | IR |  |  | Ian welcomed Nicola Stingelin, who has agreed to be Treasurer
23.03.02 | Plans for MNF Forum meeting 23 Feb
23.03.02 a | Logistics | SI | 16.03.23 | Closed | Venue checked & booked, deposit & rental paid, Refreshments & Stationery bought & invoiced. Projector required on evening.
23.03.02 b | Invitations | SI, AI, RD, IR | 16.03.23 | closed | SI has set up & launched Eventbrite invitations. AI uploaded invitation to MNF website, sent to all 440 members & supporters. RD sharing link via Waterways Flow mailings. Email to other groups; SI to find list of extended organisations. IR to invite Windsor & Cox Green Forum and RBWM Planning Policy team.
23.03.02 c | Facilitator | AI, IR | 20.3.23 | Closed | AI has recruited Maria Evans, IR & AI have met, and will have further event planning discussion with her prior to 30th
23.03.02 d | Slides, presentation | IR, AI | 20.03.23 | Closed | IR has revised & updated presentation. AI need to update presentation ready to post on MNF website
23.03.02 e | Roller banners | AI | 20.03.23 | Closed | All artwork agreed and banners are being produced by Claire Stretton - delivery to AI prior to event
23.03.02 f | online input | AI, IR | 23.03.23 | Closed | AI has updated website; IR to update FAQ; AI & IR to discuss with Maria to find best way to to be able to contribute ideas online 23rd March - 6 April
23.03.02 g | Publicity 1 | AI, MJ, AW | 20.03.23 | Closed | Banners - being produced. Leaflets & pens or pencils to be quoted & produced?
23.03.02 h | Publicity 2 | MJ, AI, | 20.03.23 | Closed | Gazebo - being produced. Maid Advertiser - Article plus full page Ad on 23.03.23. Other advertising on Social Media (Facebook, Next Door). RMWM Newsletter
23.03.02 i | After Public Meeting | SI | 05.04.23 | Closed | Photograph Post-it sheets, Collate feedback from meetings, share with management team & make available on website.
23.03.02 j | Material on tables at public meeting | SI/AI | 05.04.23 | Closed | Each table at the public meeting will have: - Banner 1 with annotated map as A3 - Banner 2 with Neighbourhood Plan process and myths - Banner 3 with policy ideas word cloud - Designation map showing wards, probably as A4
23.03.03 | Mapping - comments | MF | 20.3.23 | Open | MF has organised free trial of mapping software till 30th March. Will investigate whether it is worth subscribing to Parish Online, £750 +VAT pa Mark has confirmed he is free to use his exsting AECOM GIS software and can provide MNF mapping. Spend would require Locality agreement for Virement. Current assumption is MNF do not subscribe to Parish online this coming year. Agreement to provide map data to MNF has been signed by RBWM
23.03.04 | Gazebo | MJ, AI, | 20.3.23 | Closed | MJ has organised and ordered gazebo and table & cover. Invoiced. Now Awaiting delivery.
23.03.05 | Financial update | RD, NS, AI | 20.3.23 | Closed | Much of Locality Grant Money has been spent on publicity and materials. Any unspent money by 31.03.23 will need be returned to Locality. AI to get costs for Mailchimp and IT Support from Cavalry. RD & NS working together as M'Head Waterways are accountable body. Locality has limitations on viring money between categories. Investigate when Locality grant application for 2023/4 will open. At next management mtg, MNF will need to calculate budget for next year so we can apply for grant as soon as possible.
23.03.06 | Leaflets | AW | 30.03.23 | Closed | AW will devise MNF leaflets - "What is a neignbourhood plan?" based on Roller Banners & MNF website & contact details, and will investigate cost of production of 1000 leaflets. If acceptable will organise to be available on tables at 30th March mtg and other public events
23.03.07 | Discussion for future meetings | ALL |  |  | Apart from Waterways Funday, Festival, what other events are palnned in M'Head at which we can have a gazebo and a MNF presence.
How can we resource manpower at above events? Recruit on 30th March?
Plan budget for 23/24
Devise a Logo image which can easily be reproduced & Vector printed
MNF Public Liability Insurance (Locality grant requirement)
MNF AGM date
Meeting closed at 8.55pm
Next Management committee 12th April
Management committee meeting 12th April, Ashbury House
| Present |  |  |  | AI, SI , IR, NS, MF, MM, MJ, AW, Apologies RD
23.04.01 a | Feedback from MNF Public Meeting 30th March | IR | 30.04.23 | closed | a) IR amalgamate spreadsheet results of in-room & on-line feedback and start draft filtering of policy candidates. Aim to establish topic areas. Work with MM, AW, SI filtering group
23.04.01 b |  | AI | 18.04.23 | closed | b) AI to produce report for MNF Website and Advertiser with Key comments from Public Meeting & Online responses (closed 6th April). Also send to MNF forum members & meeting attendees
23.04.01 c |  | IR | 30.04.23 | closed | c) Deborah Mason offered to collate 'non policy' feedback and other topics. Ian to supply her with filtered, 'non-policy area' feedback
23.04.01 d |  | IR | 17.05.23 | Open | d) Ian Manketlow has agreed to regular follow up meetings and suggested 3 monthly Teams/Zoom. Ian to confirm dates.
23.04.01 e |  | TBC | TBC | closed | e) Arrange whole forum, round-table meeting to work on candidate topic groups (once we have financial resources & budget)
23.04.02 | Financial report 2022/2023 for Locality | RD, NS | 15.04.23 | Closed | Nicola and Richard have produced the End-of-Grant report, which has now been sumbitted
23.04.03 | Budget plan for 2023/2024 | NS, AW | 22.04.23 | Closed | AW has offered to assist NS with producing Budget plan. All to feedback to AW before 22 April with Budget suggestions
23.04.04 | Locality Grant application 2023/2024 | NS, RD, IR | 22.04.23 | Open | Access to Locality website is required by NS, RD, IR, so application can be made. Budget total is required. The grant application process is not yet open, but MNF should aim to be ready for when it is.
23.04.05 a | Resourcing for Waterways Day 22 April | MJ, AW, AI | 22.04.22 | Closed | AI to email members who offered to assist MNF and ask for volunteers to help MJ & AW, who will set up Gazebo and man stand during fun day. Hand out info and feedback forms to interested members of Public, Sue will create forms & provide leaflets.
23.04.05 b | Opportunities at upcoming Local events | AI | 17.05.23 | Closed | AI will research upcoming local events such as Mai Festival, at which MNF could have a presence. Decisions about who to man the events TBC once we know programme. Reprint leaflets as needed.
23.04.05 c | Ongoing Feedback | AI | 30.07.23 | Closed | As well as paper copies at events, there may be an option on MNF website to contribute views and ideas in a format similar to 30-Mar-23 meeting. AI to 'take snapshot' and review every 3 months.
23.04.08 | Public Liability Insurance | IR | 30.04.23 | Closed | In hand, it is a requirement for Locality grant - IR is working on this. Need budget figure for insurance premium. Policy can only start when we have received grant and can pay the insurance premium.
23.04.09 | Set MNF AGM date and Forum date | All | 12.04.23 | Closed | AGM will be by Zoom on 22nd June 2023. SI, AI will notify relevant people with agenda in advance of the meeting, as per constitution. Forum date TBC once we have budget.
23.04.10 | Onboarding to relieve Andrew's workload | AI | 30.04.23 | Closed | AI to invite peopole to attend Waterways Fun day to get experience of MNF, and onboard them as required. Also involve them in topic groups of interest. Poss co-opt onto committee if they are interested.
23.04.11 | Agree items for next meeting | SI | 12.05.23 | Closed | Logo Image creation; Website refresh & upgrade; Changes to our constitution (Maidenhead Waterways as accountable body); create ways to include more younger members (Rotaract, young farmers etc) to be discussed next mtg. Also NS - Procedures for handling expenses.
Next Management committee meeting 17th May 2023
Management committee meeting 17th May, The Barn
| Present |  |  |  | IR, AI, SI, MJ, MF, RD, MM, AW
23.05.01 a | Filtering feedback from Public Meeting 30.3.23 | IR | 25.05.23 | Closed | All members encouraged to review filtering feedback so far. IR, AW, MM, SI will hold further filtering mtg 23 May; estabish if policy suggestions are compatible with NPPF, BLP. Discuss how to take plans forward. Publish feedback on MNF website by 31.05.23
23.05.01 b | Next steps - RBWM contacts | AI | 30.05.23 | Open | Ian has contacted Ian Manktelow & mtg has been requested in June. Awaiting reply. No date nor agenda set yet. AI to contact Adam Bermange to make contact as new RBWM planning lead.
23.05.01 c | Next steps- Infrastructure Priorities | IR | 30.05.23 | Closed | Ian Rose will add another row in Filtering spreadsheet for Neighbourhood plan to state community priorities for s106 and CIL monies, as we have an opportunity to define it. Gov. guidance Paragraph 145 Ref ID: 25-145-20190901.
23.05.02 a | Locality & Grant application | IR | 21.05.23 | Open | Locality process for grant application not open yet, but we need to be ready to submit when it is. Ian has requested all Mgmt committee members provide ££ and commentary by 21.05.23
23.05.02 b | Budget plan for 2023/2024 - Consultants | IR |  | Closed | Ian has spoken to consultants Oneillhomer, who estimate 12 days Consultancy work costing £7,920. They are aware we need grant before they can consult, and they have stated work is unlikely to start until Aug/Sept 2023. The contract will be via our Accountable Body (Maidenhead Waterways)
23.05.02 c | Budget plan for 2023/2024 - Advertising, IT, media, website,etc | AI | 21.05.23 | Closed | Andrew to calculate costs and provide accompanying text commmentary for Grant Application: for 1) advertising, 2) publicity, 3) print/ social media, 4) Leaflets, 5) Roller banner updates 6) Graphics costs, 7) Website update, 8) MailChimp
23.05.02 d | Budget plan for 2023/2024 - Stationery and event room hire | SI | 21.05.23 | Closed | Stationery plus Events & room hire - Sue I to calculate costs, see also commentary under 23.05.05 b
23.05.02 e | Grant update | IR | 30.05.23 | Open | Ian & Nicola to establish exactly how much money in total can be given to MNF in grants , as this will inform our spending 2023/4 & beyond
23.05.03 | Process for handling expenses | IR, RD | 21.05.23 | Closed | Systems for handling expenses via Maidenhead Waterways has been circulated. Check that Nicola is satisfied this is acceptable, and if so MNF will adopt the same procedures as waterways (as accountable body)
23.05.04 | MNF AGM 22 June and next Forum meeting | SI | 24.05.23 | Closed | Sue to book & confirm Venue for AGM 22 June; AGM Calling notice must be sent out by 8th June, with agenda. Reports to be prepared in advance. We are currently expecting AGM to be face-to-face and to cover formal business and MNF resourcing of plan topic groups.
23.05.05 a | Opportunities at upcoming Local events | AI | 30.05.23 | Closed | AI is awaiting response from Robyn Bunyan at RBWM re local events that we can attend - 'Gazebo outings', including Maidenhead Festival 22.23 July. AI & AW will plan events and calculate costs.
23.05.05 b | Opportunities for Community Engagement | AI, SI, AW | 16.05.23 | Open | We propose to increase community engagement and hold 4 Plan presentation events in different parts of Maidenhead requiring 4 x Room Hire, [1 in town centre plus 3 Local Area Roadshows]. Roller banners will need to be updated for these events. In addition, "Gazebo outings" attendance at other public locations (eg Kidwells Park, Maidenhead Riverside, Nicholsons Shopping Centre, Retail Park). Grant Application "best guess" budget required to cover events.
23.05.06 | Public Liability Insurance and related cover | IR, RD, MJ | 30.05.23 | Closed | Insurance will be required for MHead Festival. Ian has had quotation, £570 for one year. RBWM require £5M public liability cover. Ian & Richard to establish threshold and liability to meet RBWM requirements, and whether single event or annual policy would be more cost effective.
23.05.07 | Logo Image Creation | AI | 24.05.23 | Closed | AI to speak to Clare Stretton re Logo creation - cost and details
23.05.08 | Website refresh and upgrade | AI | 21.05.23 | Open | AI to speak to Georgina re budget for Website refresh and upgrade. Needs to be a simple website, inexpensive, easily updated
23.05.09 | Constitution change? | IR | 30.05.23 | Closed | Ian to check whether it is is necessary to change constitution to take account of FoMW being accountable body (RD and others view: not necessary).
23.05.10 | Younger members | SI | 30.05.23 | Open | Sue to speak to Matt Sell, president of local young farmers, to see if more >18yo could be involved in MNF
23.05.11 | Ongoing Feedback | AI | 30.06.23 | Open | Andrew will collate ongoing feedback from website plus public events, review every 3 months. SI to update spreadsheets.
Next meeting; Wednesday 7th June 7pm
Management committee meeting 7th June 2023
| Present |  |  |  | AI, SI, IR, NS, MJ, RD, MM Apologies AW
23.06.01 a | AGM (& Forum Meeting) 22 June | SI | 15.06.23 | Closed | Hall Booked; invitations will be sent on 8th June. Once the Financial report is complete, it will be sent out on 15th June with the chair's report, a reminder and the updated filtering results. 6 tables chairs, water on tables. Coffee/tea for interval, Laptop & projector required. Pull up banners, MNF leaflets.
23.06.01 b | (AGM and) Forum Meeting 22. June | IR, RD | 22.06.23 | Closed | AGM 1st, then Forum meeting afterwards. After AGM, IR to explain what is planned for Forum mtg after the break. Need slides on how groups will work, nature of the policy groups and the deliverables. RD to show slides as an example of how a typical topic group, such as getting about, would work. Coffee/tea break. Reconvene after the break; subject headings will be placed on tables, people will go to the relevant table, or where there are insufficient volunteers.
23.06.01 c | AGM & Forum Meeting 22 June | IR | 15.06.23 | Closed | Ian to send the 2019 plan to the Management team
23.06.02 | Filtering process from 30th March public mtg | IR, SI | 15.06.23 | Closed | The filtering process is done, and findings have been sent out. Andrew Hill & Bob Dulson have made useful comments so IR will update spreadsheets; Sue to convert to PDF to send out with notes 15.6.23
23.06.03 | Next Steps, RBWM contacts | AI, IR | 15.06.23 | Open | AI to update email list post-election, inc. former and new councillors; AI to contact Adam Bermange as new planning lead; IR to contact Ian Manktelow to set up mtg date, due in June.
23.06.04 | Next steps, Infrastucture priorities |  |  | Closed | IR has added 'Community priorities for s106 and CIL contributions arising from development' line to topics spreadsheet, action has been closed.
23.06.05 | Locality Grant application, update | RD, NS | TBC | Open | Grant application process is still not yet open. Document has been prepared and submissions are all ready to upload data & populate the application form when it is open.
23.06.06 | Process for handling expenses |  |  | Closed | RD will send NS existing policies already in use by Maidenhead Waterways as example MNF may wish to use
23.06.07 | Public Liability insurance, progress | RD, IR | TBC | Closed | One-day insurance has been taken out in order to book pitch for Maidenehad Festival. Unfortunately as funding is not contiguous MNF are unable to renew their insurance until Locality grant is awarded.
23.06.08 | Changes to constitution? |  |  | Closed | At present It is not necessary to amend the constitution. MNF is very grateful to Maidenhead Waterways (as the accountable body) for operating it's finances. Thanks were given to RD representing MW
23.06.09 | Opportunities for MNF at local events & community engagement | ? | TBC | Open | Due to a delay in the grant process, individual members of the MNF Management committee have volunteered to donate their own money to continue MNF's vital work - eg, Public liability insurance and booking space for Maidenhead Festival; and booking a hall for AGM & forum meeting. This is considered a donation but not an acceptable way to fund MNF Activities. Until a grant is awarded, we are unable to further engage with the public in any way. Donations of member's own money are to be recorded in MNF accounts.
23.06.10 | Logo image Creation and Website refresh | AI | TBC | Open | AI has had quotes for both. It is decided not to pursue Logo creation. We will refresh the MNF Website once a grant is awarded. At present MNF have no funds to pay for this.
23.06.11 | Younger members | SI, MJ | 1.9.23 | Open | SI is in discussion with Matt Sell, president of local Young Farmers, and & MJ with Matthew Burdett President of Rotaract, in order to find ways to engage more younger residents. Further updates by September.
23.06.12 | Finance | IR, SI, NS | ASAP | Open | IR to obtain NatWest Bank statement via former treasurer, Bob Beauchamp, and to arrange for transfer signatories to NS (treasurer) and SI (secretary).
23.06.13 | Neighbourhood Plan Policies and SPDs (Supplementary Planning Documents) | IR |  | Open | MNF policy not is allowed to contradict BLP or NPPF, but to what extent do Maidenhead Neighbourhood Plan policies have to align with existing SPDs (some of which are Borough-wide)?
Next AGM & Forum Meeting 22 June 7.30pm URC
Next MNF committee meeting 19th July 2023
Management committee meeting 19th July 2023
| Present |  |  |  | AI, SI, IR, NS, RD, MM, AW, MF apologies MJ
23.07.01 | Feedback from AGM & Forum Meeting 22 June |  |  | Closed | Both AGM and Forum meeting attended by MNF, all objectives met
23.07.02 | Topic group setup and progress to date |  |  |  | All groups have now met and are researching relevant documentation.
23.07.02 a | Biodiversity and Climate | MF | 16.08.23 | Open | Biodiversity & Climate: 2 groups will work together as there are many shared topics, Donna Stimson will be invited to the next full topic group MNF mtg. Bioregional Sustainability SPD (currently in draft form) is soon to be published and will supersede the Interim sustainability Statement. It will be a very useful starting point. DS has a lot of useful contacts in Biodiversity arena and will be a very helpful group member. The two groups will remain under separate leaderships, Donna and Mark.
23.07.02 b | Housing | MM | 29.08.23 | Open | Housing. Discussion about composition of the group, which was weighted towards Windsor and CLT, but the group is expected to cover all the topics, and will meet again 29.8. Judith Littlewood has a great deal of knowledge in this field, and will be a very valuable member of the group, assisting MM.
23.07.02 c | Built Heritage | AI, NS | 19.08.23 | Open | Built Heritage. A local heritage list of assets (outside Conservation Areas) needs to be created. RBWM Heritage Strategy Report is overdue and will be published soon. We will work together, align and collaborate plans. It is not yet clear who manages the content of the local heritage list. NS to contact Conservation Officer, AI to contact Clare Price & group will refer to Heritage list to evidence our Neighbourhood Plan policies
23.02.07 d | Design | AW | 16.08.23 | Open | Design. SPD is not policy but material consideration. We can't do a lot in town centre, but there could be a 'Maidenhead Design Guide' based on ideas from Datchet NP. More research is required before next mtg
23.07.02 e | Getting Around | RD. IR | 16.08.23 | Open | Getting Around. Although we are restricted in some areas of Transport Policy (for example we cannot set bus routes or frequencies), we can write a 'vision Statement' regarding Public Transport. Ideas and vision need to be documented. In other areas such as cycle routes and car parking we may be able to write policy.
23.07.03 | Locality Grant application, update | AI, SI, AW | 01.08.23 | Closed | Not open yet, anywhere in England. AI to follow up with TM, SI to Michael Grove. AW will contact Locality.
23.07.04 a | Finance - Nat West | NS, SI, AI | 01.09.23 | Open | Nat West - Current contact is Bob Beauchamp, the previous treasurer. We need to update to NS, with new signatories NS, AI, SI. Not critical until we have funding money.
23.07.04 b | MNF – MW agreement | NS, RD, IR |  | Closed | Agreeent with MW as accountable body has been signed.
23.07.04 c | MC Personal contributions and expenditure | SI |  | Open | a) SI to collate info on MNF money spent since our grant expired: Booking Mai Festival £20, Single event Insurance £70, URC Hall £72, b) In the absence of any Grant or funding, Members of the Management Committee have contributed personally to essential expenditures and these should be listed and recorded as donations. c) To date, RD has been reimbursed for Insurance by all MC members. The status for other expenditures needs to be clarified and recorded. d) This cannot be allowed to continue, and no more events can be planned or booked. When/if we get funding the money cannot be retrospectively repaid to MC members.
23.07.04 d | Future Plans |  |  | Closed | We must consider other sources of income such as applying for grants & funding, charging MNF members fees, etc. At present, Public Consultation is on hold. No future plans can be made, No funding, no budget. no insurance. No Public Engagement.
23.07.05 | Feedback from M'head Town Forum Meeting 17.7 | AI |  | Closed | IR & AI attended and presented to Maidenhead Town Forum. Explained more about Neighbourhood Plan. Useful contacts with new councillors were made.
23.07.06 | Plans for Maidenhead Festival | AI |  | Closed | In hand, Stand and materials on Sunday, all logistics as per AI emails.
23.07.07 | Draft 2019 Plan update | IR, RD | Ongoing | Open | IR to send an editable Word Doc with 2019 Draft Plan. RD has offered to update the town overview section. RD offered to monitor relevant statistics based on the 2021 census data.
Meeting closed at 09.10pm
Extra MNF Management cttee Zoom mtg 8.8.23
| Present |  |  |  | IR, AI, SI, NS, RD, AW, MJ
23.08.01 | Locality Grant Application | IR, NS | 12.08.23 | Closed | Grant Application process is now open, MNF management group met (via Zoom) to discuss 4 components which require formal estimates. Further items require budget reduction. Cttee is required to approve prior to submission.
23.08.01 a | Neighbourhood Plan Consultancy |  |  | Closed | IR has previously spoken to Oneillhomer, who estimate 12 days of Consultancy work costing £7,920. Named consultants, Qualifications and cost is required on grant application. Cttee approved this
23.08.01 b | Facilitation costs |  |  | Closed | AI now has a formal estimate of costs, will be added to grant application
23.08.01 c | Social Media Training | AI | 12.08.23 | Closed | Formal estimate is required for grant application. If not rec'd by 11 August, then the £100 budget will be listed as 'project cost'
23.08.01 d | Website refresh and upgrade | AI | 12.08.23 | Closed | Formal estimate is required for grant application. Ai to chase supplier for £200 Budget Estimate, to be added to grant application.
23.08.01 e | Insurance |  |  | Closed | Cost of Insurance premium was discussed and approved by committee as it is pre-requisite to attend events for public engagement
23.08.01 f | All other items on Grant application |  |  | Closed | Budgets for room hire, stationery etc have been reduced, approved, and are now ready to go on Grant application.
23.08.01 g | Grant application | IR, NS | 12.08.23 | Closed | subject to estimates, grant application submission is now ready
Next meeting 7pm Wednesday 16th August 2023. Ashbury House
Management Cttee Mtg 16th August 2023
| Present |  |  |  | AI, SI, IR, NS, MF, MJ,RD, AW, Apologies MM & Donna Stimpson
23.08.01 a | Locality Grant application, update and Housing Needs Assessment | IR, MM | 30.08.23 | Open | The grant funding app'n was submitted by IR, and although there was no official receipt, NS had a phone call from David Chapman asking about Housing Needs Assessment. IR & MM will set up a conversation with David Chapman (Diagnostic call), and clarify if housing needs is based on current info and BLP or historical numbers. IR will reiterate that an oversupply of flats (and housing mix) is of concern to Mai Residents. Post-meeting note: Grant Application acknowledgement e-mail now received from Locality
23.08.02 a | Feedback from IR & AI call with RBWM Planning Policy team. | IR | 30.08.23 | Open | Teams mtg on 08.08.23 IR, AI, Ian Manketlow and Ian Motuel. They were impressed with MNF activity so far, but surprised no mention of business or enterprise in topic groups. Agreed to continue 3-monthly contact, want confirmation of work schedule and timescales -MNF asked for use of meeting room no cost. (no funds)
23.08.02 b | Work Plan Schedule | AI, AW, NS |  | Open | AW to provide an updated schedule based on the late award of funding grant for FY23/24. Grant Window is to 31st March 24, before which any funding needs to be spent. Prior to draft plans, further engagement with public to ensure they are aware of progress and topics before AGM, June '24.
23.08.03 | Topic group progress to date | DS |  | Open | Environment - Donna invited to next meeting to report progress, MF preparing map of Green Intrastructure
|  | AI, NS |  | Open | Built Heritage- Team have met and researched relevant documents to date. NS still awaiting response from RBWM re Heritage Listings. AI to contact Matthew Shaw re previous heritage photos
|  | MF |  | Open | Climate - RBWM Interim Statement was good, but draft sustainability SPD disappointing. RBWM Net Zero aspiration is 2050 in line with National Policy. In NP, will try to insist on on-site Net Zero, Want to be more ambitious than 2050 national target, which may then justify ambitious NP policies.
|  | AW |  | Open | Design - Will meet next on 18.08. They want to co-opt members with relevant experience. MF to provide examples of Design to AW
|  | RD, IR |  | Open | Getting Around. 2019 plan had good policies, but plans are restricted in some areas of Transport Policy, but CAN link our plan with existing policies eg LCWIP (Local Cycle and Walking Infrastructure Plans). IR to provide link to RBWM LCWIP. Post meeting note: IR has provided this document
|  | MM |  | Open | Housing, MM was absent but reported that a mtg is planned 29.08. Also ongoing discussions about social/ affordable housing from 2 co-opted members and Windsor residents & their invaluable contributions.
23.08.04 | Finance – Nat West |  |  | Open | Low priority. The Locality grant money if received would go into the MW (accountable body) account.
23.08.05 | Feedback from Maidenhead Festival | AI, NS | 20.09.23 | Open | Good to be seen to be present, but not much interest from public at Mai Festival. AI to investigate further opportunities for 'gazebo outings' inc farmers market, High St market. NS to investigate contact with residents' Associations. Perhaps larger M'head Plan poster to use with Gazebo.
23.08.06 a | AOB - mtg AI with Steph James | IR, MF, AW | 30.08.23 | Open | Steph James is strategic lead for Economic development for the area. AI suggested Telecon with IR and MF to discuss any economic areas that could become policy in NP. AW to research any economic development policies in other neighborhood plans
23.08.06 b | 2020 Census Data | RD |  | Open | RD has updated relevant local data based on latest Census, re housing mix and degree of deprivation, and has offered to analyse more data for specific topic groups as required.
Next meeting 7pm Wednesday 20th Sept, Venue TBC
Management Cttee Mtg 20 Sept 2023 at Ashbury House
| Present |  |  |  | IR, AI, SI, RD, MF, MJ,NS, AW, DS Apologies MM,
23.09.01 | Locality Grant application, update and Housing Needs Assessment | IR | 4.10.23 | Open | Grant not yet rec'd (4 wks). Tech Support package 'inception mtg' booked 4.10.23, MM, IR, Judith Littlewood to attend
23.09.02 | Topic group progress to date | MF |  | Open | Climate: RBWM net zero target still 2050. MNF would like to be more ambitious, but can't rely on RBWM changing date. MNF to go ahead with Mark's Energy based operational net-zero policy for new developments (met by having good level of insulation, heat pumps, solar panels, etc)
|  | AI |  | Open | Built Heritage: Policy is already in BLP, but Local Heritage List doesn't yet exist for Maidenhead and all policies are confined to Conservation Areas and Listed buildings. NS is loooking at Heritage Listing Criteria, Public nominations; AI working with Matthew Shaw to find way to record & map all relevant Heritage sites (buildings, spaces, views, features). MF will provide a map of all buildings built prior to WWI which are still standing . RBWM has not responded but is being kept informed of progress
|  | RD |  | Open | Getting about: MNF agreed that car remains key component of local transport network and ownership per household is unchanged since 2011 census. Neighbourhood plan needs to encourage car sharing clubs, realistic car park standards (weight, size etc) and parking policy.
|  | AW |  | Open | Design. 2010 Townscape assessment is a helpful starter for design guide, although certain areas have changed use, such as industrial to residential. Peter Knott to superimpose maps, MF to supply basemaps. AI & IR to check with Ian Motuel and Ian Manktelow to check whether RBWM intend to update Townscape Assessment and ask if there is any work on a master plan for town centre, (as per BLP recommendation).
|  | DS, SI |  | Open | Biodiversity: Recommended DS to work with MF as a great deal of overlap. SI to send DS filtering spreadsheets. IR to send "starter pack" including 2019 draft which has list of Green Spaces. DS will check other NPs with similar demographics to see what biodiversity policies they have.
|  | MM |  | Open | Housing: MM trying to relinquish lead role, Judith Littlewood v helpful and knowledgeable. Technical support package on housing has been initiated, Inception call booked 4 Oct. Group want to set a policy for housing mix (ie ratio of housing sizes rather than absolute number of properties - too many studio & 1 bed homes and insufficient 3 or 4 bed properties). MNF plan period stated to RBWM as 15 years. RBWM will assess housing need for plan area. 70% of RBWM allocated new homes are planned in Maidenhead, but MNF cannot change BLP allocations regardless of residents views.
23.09.03 | Public engagement opportunities? | AI | 30.09.23 | Open | Without funding (and therefore insurance) we are unable to attend Town Fair 21st Oct, Nicholson Craft Coop, However, Donna has offered the use of Building Bridges Hub as a venue for public engagement and already has public liability insurance. MNF is very grateful, will plan some additional dates.
23.09.04 | Feedback from IR & AI call with RBWM Planning Policy team. | AI, IR | 30.10.23 | Open | No response yet about availability of meeting room at no cost. (3 monthly) follow-up call Ian Manktelow and Ian Motuel expected to be in Nov.
23.09.05 | Work Plan Schedule | AW | 30.10.23 | Open | As funding has been delayed, the work schedule has also been delayed. Concerns that expected public engagement activities have not occurred as no funds available for room hire, insurance etc. See above 23.09.05 DS offered the use of her Building Bridges Hub in Nicholson's Centre for some public interaction Thank you DS from MNF.
23.09.06 | Economic Development ideas? |  |  | Closed | No feedback yet from Steph James following her discussion with AI.
23.09.07 | AOB | AI | 30.09.23 | Open | AI will contact membership of Eco Action members and ask for volunteers to help write eco-policy
Date of next meeting, Oct 18th 7pm
Management Cttee Mtg 18th October 2023 at Ashbury House
| Present |  |  |  | IR, AI, SI, RD, MF, MJ, MM, NS, Apologies DS AW . Judith Littlewood also attended and has been invited to future MNF meetings.
23.10.01 | Locality Grant application update | IR, NS | 24.10.23 | Open | Grant offer made, but as yet we have not received money from Groundwork as we have been unable to access the portal to accept the offer. This will be done very soon. In light of offer of grant, Ian Rose has offered to pay insurance premium of £312.40 to cover £5m public licabilty insurance (which will allow MNF to book events) for one year insurance to Oct 2024. this was unanamously approved by commitee, and Ian will reclaim once grant is paid.(update 19.10.23 - offer has been accepted, MNF now awaiting payment)
23.10.02 | Topic group progress to date | MF, SI | 30.10.23 | Open | Climate: RBWM net zero target still 2050. MNF would like to be more ambitious than RBWM SPD. Draft Policy Documents and all other key documents will be circulated to all members of all topic groups once SPD consultation is over. SI to create a distribution list.
|  | MM, JL |  | Open | Housing; Currently MM, Judith Littlewood and David Snelgar have been most active. Awaiting housing needs assessment (HNA) in New Year. Group will then be able to start work on Local Maidenhead Housing Policy dcoument, using information about HNA, social housing, affordable housing, and degree of deprivation. Also awaiting waiting list numbers for affordable housing, rental, shared ownership etc for Maidenhead
|  |  |  | Open | 12 Consultant's days were planned in budget, and initially expected to be helping to create housing policy, but other areas for consideration include design, streetscape. Need to define scope of work with O'Neil Homer & possibly adjust # days as day rate has increased from £550+VAT to £578+VAT.
|  |  |  | Open | Group will meet again at end of Nov in order to involve and engage other members of Topic group, and will report back to MNF committee afterwards.
|  | AI, NS, MJ |  | Open | Built heritage This is not just listed buildings, but also Include space, view, cone of vision. Within any given character area, are there valued assets. RBWM are now looking at listings and heritage buildings
|  |  |  | open | Group have researched documents and looking for asets which just miss out on being listed or conservation areas. Have met Paul Seddon (Archaeological Team), to share insights.
|  |  |  | open | AI Meeting planned with Windsor built heritage specialist Alison Logan for advice.
|  | RD |  | Open | Getting about: An udated 2019 policy would fit our brief regarding cycle, parking, etc. In addition, Topic Group wants to include connectivity at Rlwy station & intersections, and this could could have planning policy attached to it. Any new development directed towards existing transport networks and intersection hubs.
|  | DS |  | Open | Biodiversity: no new actions
|  | AW |  | Open | Design No new actions
|  | IR | 30.10.23 | Open | IR will take 2019 Draft Plan, make editotorial comment, adjust headings to match current topic groups, and send to all MNF Team leaders for comments, track changes.
23.20.03 | Public engagement opportunities? | AI | 30.10.23 | Open | As we have grant offer and therefore can get insurance, we will no longer go ahead with a publicity event at Building Bridges Hub (but thank you to Donna for offering the space). We will instead look for Gazebo Outing opportunities, such as Nicholson Centre, Maidenehad High Street at weekend. AI to speak to Robyn Bunyan & Town Centre team, to book space. AI to create leaflets to inform public what has been done so far, and progress that has been made.
Date of next meeting, Nov 15th 7pm

## Sheet2
i | r
A | i
s | i
m | j
m | m
d | s
n | s
a | w
R | D
m | f